## MAIN
GAIL (India) Limited (A Government of India Undertaking - A Maharatna Company)
MECHANICAL DEPARTMENT, VIJAIPUR
MONTHLY PERFORMANCE REPORT JULY 2024
MAINTENANCE COMPLIANCE
Planned Preventive Maintenance (PM02)
| Plant | PLANNED | EXECUTED
| C2C3 | 44 | 44
| LPG | 32 | 32
| HVJ | 36 | 36
Un-planned Maintenance (PM01)
| Plant | PLANNED | EXECUTED
| C2C3 | 92 | 92
| LPG | 145 | 145
| HVJ | 43 | 43
Breakdown Maintenance
| Plant | No. of Breakdown Jobs carried out | Short Description of Job
| C2C3 | 2 | Casing leak in 16-PA-107 B, LP Compressor-B Third stage high vibration failure
| LPG | 1 | Thermax VAM tripped due to PT malfunctioning
| HVJ | 2 | DVPL EOT WHEEL REPLACEMENT, HRSG-C, Sample line de-chocked work
5
Jobs Hold for Shutdown
| Plant | No. of Jobs hold | Short Description of Job
| C2C3 | 0
| LPG | 0
| HVJ | 0
0
VIBRATION MONITORING
| Plant | No. of Equipment Scheduled | No. of Equipment Monitored (Executed) | Reasons for Equipment not monitored.
| C2C3 | 199 | 196 | LP compressor-B Breakdown, LEAN AMINE CHARGE PUMP-D in stopped conditon, DIESEL ENGINE -A (FWPH) under maintenance.
| LPG | 287 | 274 | MACHINE UNDER SHUT DOWN - 08 No. 1) PRU-1 GT, 2) PRU-1 COMPR, 3) PRU-2 GT, 4) PRU-2 COMPR, 5) DED F . W. PUMP - B, 6) RAIL LDNG PUMP - B, 7) NAPTHA PUMP-B (PH-2), 8) NAPTHA PUMP-A (PH-2) MACHINE UNDER MAINTENANCE - 05 No 1) STP-2 SDM PUMP- C, 2) STP-2 SUBMERSIBAL PUMP-2, 3) STP-1 RECIRCULATION PUMP- 2, 4) COOLING TOWER FAN-3 AUDITORIUM BLD, 5) COND WATER PUMP-4 AUDITORIUM BLD,
| HVJ | 69 | 63 | 1.GTC M/L-A GG STANDBY 2. GTC M/L-A COMP STANDBY 3. VDPL GTC-A GG STANDBY 4.VDPL GTC-A COMP STANDBY 5. VDPL GTC-A LOC-2 MAINTENANCE 6. VDPL IA COMP RADIATOR FAN-1
|  | No. of Euipment With Normal Health | Health Index
| C2C3 | 196 | 100%
| LPG | 271 | 98.91%
| HVJ | 61 | 96.83%
|  | No. of Equipment With Critical Health | Critical Index
| C2C3 | 0 | 0%
| LPG | 3 | 1.095%
| HVJ | 2 | 3.175%
|  | Corrective Actions Initiated | Corrective Actions Pending | Short Description of Issue and Action taken/ Reasons for actions pending
| C2C3 | 0 | 0 | NA
| LPG | 1 | 2 | 1) STP-1 SUBMERSIBAL PUMP-1 : MOTOR vibration problem found, concern dept. has been informed. 2) HVAC COMPRESSOR-1 : Internal Bearing inspection to be done, status : Pending. 3) CONDENSATE WATER PUMP-1 : Job completed (Problem: Shaft damage)
| HVJ | 2 | 0 | LOOSENESS OF BELT AND MISLAIGNMENT IN DVPL GAC-1 & DVPL LOC-1. GREASING, ALIGNMENT AND BELT TIGHTENING ENSURED |  | looseness of belt and mislaignment in dvpl gac-1 & dvpl loc-1. greasing, alignment and belt tightening ensured
LUBE OIL ANALYSIS (Monthly Moisture Analysis)
| Plant | No. Scheduled for analysis | No. of Samples Analysed
| C2C3 | 21 | 21
| LPG | 8 | 8
| HVJ | 29 | 29
|  | Corrective Actions Required | Corrective Actions Taken | Short Description of Issues & Action Taken
| C2C3 | 0 | 0
| LPG | 0 | 0
| HVJ | 6 | 5 | 1. K01A higher viscosity. Complete lube oil replacement done.Resampling and test in GAIL lab done. Found within range 2. K01C higher viscosity. Resampling and test in GAIL lab done. Found within range. sample resent to Petrolabs to retest the oil sample 3. K01E higher viscosity. Resampling and test in GAIL lab done. Found within range.sample resent to Petrolabs to retest the oil sample 4. K02B higher viscosity- Machine running. Complete lube oil replacement to be done. 5. HVJ DEG- Higher moisture- Centrifuge was run to remove moisture & then, resampling was done in GAIL laboratory and moisture content found to be within range 6.VDPL DEG- Higher moisture- Centrifuge was run to remove moisture & then, resampling was done in GAIL laboratory and moisture content found to be within range
SPARES MANAGMENT
| Plant | Indents Scheduled for Review in this month | No. of PR Raised in this month | Cumul. No. of Indents Scheduled for Review till this month in F.Y. 24-25 | Cumul. No. of PR Raised till this month in F.Y. 24-25
| C2C3 | 1 | 2 | 28 | 5
| LPG | 8 | 3 | 19 | 10
| HVJ | 4 | 1 | 9 | 3
New Contracts
|  | No. of SR Raised | Cumul. No. of SR Raised till this month in F.Y. 24-25 | Cumul. No. of PO placed till this month in F.Y. 24-25
| C2C3 | 0 | 5 | 1
| LPG | 1 | 3 | 2
| HVJ | 1 | 1 | 0
Running Contracts
|  | Total Current Running Contracts | Contracts requiring Renewal (& expiring in this/next six months) | Contracts Expired in this month (& not requiring renewal)
| C2C3 | 48 | 2 | 0
| LPG | 34 | 5 | 1
| HVJ | 24 | 6 | 2
Contracts with Manpower at Site
|  | No. of Contracts | Contracts with valid Workers Insurance/ CPBG
| C2C3 | 7 | 7 | AMC, Crane, Painting, NDT, Fabrication, Insulation, HVAC
| LPG | 11 | 11 | 1) Mech maint. AMC, 2) PAINTING AMC, 3) FABRICATION AMC, 4) FWT painting, 5) Railway AMC, 6) NDT AMC, 7) HVAC maint. AMC, 8) Insulation AMC, 9) Assistance for inspection of Horton Spher, 10) LPG SPHERE: EXTERNAL MECHANICAL JOBS, 11) STATUTORY INSPECTION, RE-CERTIFICATION OF LPG & PROPANE SPHERES AS PER SMPV (U) RULES 2016, PESO AND INSTALLATION OF STILLWELL & SUPPORT FOR LTs IN PROPANE SPHERES AT GAIL INDIA LTD., VIJAIPUR.
| HVJ | 5 | 5
Health Monitoring of Contracts (Quarterly)
|  | No. of Contracts (over 1Cr.) | No. of Contracts with Issues
| C2C3 | 3 | 0 | AMC, Painting, Crane,
| LPG | 2 | 0 | AMC, Painting
| HVJ | 0 | 0
Closed Contracts (Quarterly)
|  | No. of Contracts completed as per Schedule in previous qtr | Contracts with Final Bill Cleared | Contracts Closed in SAP
| C2C3 | 3 | 2 | 0
| LPG | 3 | 2 | 0
| HVJ | 2 | 0 | 0
IMS COMPLIANCE
| Plant | No. of Observation | Complied | Pending
| C2C3 | 0 | 0 | 0
| LPG | 0 | 0 | 0
| HVJ | 0 | 0 | 0
|  | 0 |  | 0
AUDIT COMPLIANCE
| Audit Description | Plant | No. of Observation | Complied | Pending
| Internal Safety Audit PNGRB | 5020
| Technical Audit | 5020
| Ext. Sustainability Audit | 5020, 6020, 3015 | 1 | 1 | 0
| Internal Safety Audit PNGRB | 6020
0
GATE PASS DETAILS
|  | New Gate Pass Created in this month | Gate Pass open till last month | Gate Pass Closed in this month | Total current open Gate Pass
| C2C3 | 2 | 3 | 0 | 5
| LPG | 3 | 10 | 1 | 12
| HVJ | 1 | 8 | 1 | 8
E-FILE STATS
|  | No. of e-Files Initiated | No. of e-Files Approved out of initiated | No. of e-Files Closed out of Approved
| C2C3 | 15 | 14 | 14
| LPG | 5 | 3 | 0
| HVJ | 2 | 0 | 0
INVOICING COMPLIANCE
| Plant | No. of Invoice Received by EIC | No. of Invoice Processed by EIC
| C2C3 | 16 | 15
| LPG | 3 | 3
| HVJ | 5 | 2
SAFETY COMPLIANCE
| Plant | Near Miss |  | Safety Observations
|  | Allotted | Reported | Allotted | Reported
| C2C3 | 1 | 1 | 2 | 2
| LPG | 0 | 0 | 3 | 0
| HVJ | 1 | 2 | 2 | 1
LUBE OIL CONSUMPTION
|  | Lube Oil Name | C2C3 Consumption (Ltrs.) | C2C3 Fresh Issued from Store (Ltrs.)
| C2C3 | SP 46 G | 210 | 0
|  | SP 32 | 5 | 0
|  | SS 32 | 15 | 0
|  | 15W40 | 5 | 0
|  | SS 46 | 150 | 210
|  | SS 150 | 45 | 210
| LPG | SERVO PRIME 32T
SERVO PRIME 68
SERVO SYSTEM 68
SERVO MESH SP 320
SERVO PRESS 68
SERVO GEAR HP 140
Servo trans fluid A
SERVO SYSTEM 46
SERVO System HLP68
SERVO FRIZ 68
SERVOS PREMIUM CF 4 15W/40
| HVJ | Mobilejet-2
Tribunol 46
EP 32
HAZARDOUS WASTE HADED OVER IN JANUARY
| Plant | Item Description | Weight (kg) | Total Weight (kg)
| C2C3 | Metal | 4970 | 5810
|  | Non -Metal | 840
Lube Oil
| LPG | Metal - MS |  | 0 |  | C2C3 | 5810
|  | Non Metal - Plastic |  |  |  | LPG | 0
| HVJ | Metal - Insulation | 220 | 580 |  | HVJ | 580
|  | Non Metal - Cotton Waste | 360 | 360
|  | Approved (IN Lacs) |  | Utilisation (in Lacs)
|  | RE-2023-24 | BE 2024-25 | 2024-07-01 | Cumulative - F.Y. 2024-25 | For S&S filter plant then PO then date |  | June
| C2C3 - R&M | 605.6 | 528.65 | 28.1 | 467.8 | For R&M filter CPF & delete CPF then plant then date |  | 211.61 | 439.7
| C2C3 - S&S | 456.3 | 505.6 | 11.28 | 39.4179 |  |  | 19.09 | 28.1379
| C2C3 - CAPEX (O&M) | 2594 | 1263 | 0 | 730.8588 |  |  | 67.76 | 730.8588
| LPG - R&M | 305.6 | 324.98 | 10.53 | 85.3679 |  |  | 70.64 | 74.8379
| LPG - S&S | 337.5 | 331.2 | 0.747 | 36.543 |  |  | 16.47 | 35.796
| LPG - CAPEX (O&M) | 6185 | 8153 | 0 | 1327.5362 |  |  | 28.71 | 1327.5362
| HVJ - R&M | 135.45 | 137.37 | 0.4088 | 50.194 |  |  | 48.03 | 49.7852
| HVJ - S&S | 183.72 | 250.38 | 1.53 | 25.7801 |  |  | 21.85 | 24.2501
| HVJ - CAPEX (O&M) | 7946 | 13082 | 0 | 405.1498 |  |  | 0 | 405.1498
| Knowledge Sharing Sessions Details |  |  | Safety talks by EIC
| Plant | No. of session is this month |  | Plant | No. of safety talks conducted in this month
| C2C3 | 0 |  | C2C3 | 0
| LPG | 0 |  | LPG | 1
| HVJ | 0 |  | HVJ | 1
| RTI Queries |  |  | EDMS
| Queries In this month | 1 |  | Plant | No. of Files EDMS Done
| Replies Given in this month | 1 |  | C2C3 | 0
| Total Rreplies given in F.Y. 24-25 | 2 |  | LPG | 48
|  |  |  | HVJ | 0
LUBE OIL CONSUMPTION
|  | Lube Oil Name | C2C3 Consumption (Ltrs.) | C2C3 Fresh Issued from Store (Ltrs.)
|  | SP 46 G | 210 | 0
|  | SP 32 | 845 | 630
|  | SP 68 | 305 | 420
|  | 15W40 | 35 | 0
|  | SS 32 | 15 | 0
|  | SS 46 | 150 | 210
|  | SS 320 | 60 | 0
|  | SS 150 | 45 | 210
|  | Mobilejet-2 | 446 | 210
|  | SS 68 | 55 | 0
|  | SS 220 | 10 | 0
|  | Servo Mesh SP 320 | 10 | 0
|  | Servo Press 68 | 20 | 0
|  | Servo CUT S | 5 | 0
|  | SS HLP 68 | 20 | 0
|  | Servo Gem EP2 | 60 | 0
|  | SERVO GEAR HP 90 | 40 | 0

## PLOTS
|  | 5 | Breakdown Maintenance
|  | 0 | Jobs in This Month Hold for Shutdown
0 | IMS Audit Observations
0 | Audit Points Compliance Pendine
This chart isn't available in your version of Excel. Editing this shape or saving this workbook into a different file format will permanently break the chart.
No. of Orders
No. of Orders
No. of
Corrective Actions
This chart isn't available in your version of Excel. Editing this shape or saving this workbook into a different file format will permanently break the chart.
5
MEETINGS
CONDUCTED
MEETING
DATES
16.01.2024
07.03.2024
28.04.2024
01.06.2024 26.06.2024
CONDUCTED
NOT CONDUCTED

## Major Highlights
Major Highlights for July 2024
Date | Description | NOTE: Add short descriptions of Major Meetings, Presentations, Awards, Engine testings, etc.
2024-07-31 | H2 Blending in SGT 700 - Meeting with M/s Siemens
2024-07-18 | Team PRAYAAS from Mechanical Department selected as 1st Runner Up for CMD Trophy Award of 2022-23
2024-07-27 | Shipment of M/s Solar Turbines make Titan130S Gas Engine Assembly Serial No. 0081L installed in DVPL-B skid for Overhauling
2024-07-24 | VC concluded for water glycol chilling system required for Naphtha vapor recovery during tanker loading.
2024-07-27 | Final TBA done for Procurement of Non-sparking tools.
2024-07-30 | TBA for Hiring Crane Services (300MT Crane)
2024-07-08 | Performance testing of RB211 24GT DLE Gas Generator Serial No. 1890-2046 at M/s RWG, UK facility
19-07-2024 | SOP for GPU and HVJ Station was approved by CGM (O&M-GPU & HVJ)
18.07.2024 | TBA for REFURBISHMENT OF JOHN CRANE MAKE DRY GAS SEALS (DGS) INSTALLED IN SIEMENS MAKE HP LEAN GAS COMPRESSOR (LGC) UNITS OF C2C3 PLANT DONE
26.07.2024 | Procurement of Instrument and Seal Air coolers for Gas Turbines of Lean gas compressor (LGC) units installed at C2C3 Recovery Plant approved and Indent Raised for INR 1.22 CR
23.07.2024 | Procurement of filter elements for Air Intake System of Gas Turbines installed at C2C3 Plant approved and Indent Raised for INR 5.98 CR
25.07.2024 | Release orders for spares and services worth INR 6.05CR for calendar Year 2024 issued against Long-Term Planning (LTP) contract for Lean Gas Compressor package maintenance
30.07.2024 | Procurement of Regenerator column (16-CC-102) Internals installed in C2C3 Recovery Plant GSU at GAIL Vijaipur approved and Indent Raised for INR 3.8 CR
30.07.2024 | Kirloskar Ebara Pumps Limited Mr. Rohit Upadhye Sr. Manager –Turbine CSD visited for KEPL steam turbines performance review and O&M effectiveness enhancement possibilities discussion
31.07.2024 | Hydrogen capability in SGT 700 presentation by Siemens Energy Sweden team
05.07.2024 : | VC for discussion on FFS Report of LPG Sphere H with EIL
11.07.2024 : | VC for discussion on RMS report of LPG Sphere H with EIL, TUV SUD
15.07.2024 : | PRE-TENDER MEETING FOR HIRING SERVICES FOR CARRYING OUT REPARING JOB AND ASSOCIATED NDT INSPECTION, STATUTORY INSPECTION, HYDROTESTING & MODIFICATION OF STILLWELL OF LPG SPHERE H AT GAIL VIJAIPUR with prospective bidders
17.07.2024 : | PRE-BID MEET: GEM BID NO.: GEM/2024/B/5147779 DATED 10.07.2024 - HIRING SERVICES FOR STATUTORY INSPECTION OF PROCESS PIPELINE, PRESSURE VESSELS/EQUIPMENT & LIFTING TOOLS & TACKLES AT GAIL, VIJAIPUR FOR A PERIOD OF TWO YEARS with prospective bidders.
09.07.2024 : | Meeting with Dy. CCOE regarding Sphere-H repair job at PESO office Nagpur.
|  |  | 1 | 2024-07-03 | Meeting related to Electrification of Gas Turbine drive in Branch line K02A Skid carried out.
03/05/09/22/24.07.2024 | Meeting related to Electrification of Gas Turbine drive in Branch line K02A Skid: VC done with M/s Siemens team for automation, seal oil pumps, foundation, techincal quieries and major items delivery scheduled for Electric Drive Project held on 03.07.24, 05.07.24, 09.07.24, 22.07.24, 24.07.24 |  | 2 | 2024-07-05 | VC for discussion on FFS Report of LPG Sphere H with EIL
25/26.07.2024 | FCV installation in VAPL line: Child PO awarded to M./s Lyons for PMC service, site visit done for P&ID, Design basis etc. held on 25.07.24 & 26.07.24 |  | 3 | 2024-07-08 | Performance Testing RB211 24GT DLE Gas Generator Serial No 1890-2046 at M/s RWG, UK.
25/26.07.2024 | VDPL Vent Recovery as GTG/GTCs fuel: Child PO awarded to M./s Lyons for PMC service, P&ID revision-2 received, design basis received, site visit done for GAD preparation held on 25.07.24 & 26.07.24 |  | 4 | 2024-07-09 | Meeting with Dy. CCOE regarding Sphere-H repair job at PESO office Nagpur.
27/28/30.07.2024 | Technical discussion done with M/s President Engineering for Anchor Bolts manufacturing and test for Electric Drive Project held on 27.07.24, 28.07.24 & 30.07.24 |  | 5 | 2024-07-11 | VC for discussion on RMS report of LPG Sphere H with EIL, TUV SUD
27.07.2024 | Technical discussion done with M/s Aeroflex for Felxible Hose sizes and specifications for Electric Drive Project |  | 6 | 2024-07-15 | PRE-TENDER MEETING FOR HIRING SERVICES FOR CARRYING OUT REPARING JOB OF LPG SPHERE H AT GAIL VIJAIPUR with prospective bidders.
30.07.2024 | BEC TBA Done for 27 Nos bidders for procurement of 02 Inch Gate vlave for utility cooridor work. |  | 7 | 2024-07-17 | PRE-BID MEETING FOR HIRING SERVICES FOR STATUTORY INSPECTION OF PROCESS PIPELINES, etc. with prospective bidders.
08.07.2024 | Performance Testing RB211 24GT DLE Gas Generator Serial No 1890-2046 at M/s RWG, UK. |  | 8 | 2024-07-17 | Team meeting with M/s RWG, UK in regards to the installation & comissioning of RB-211 24 GT DLE engine at VDPL GTC-C.
17.07.2024 | Team meeting with M/s RWG, UK in regards to the installation & comissioning of RB-211 24 GT DLE engine at VDPL GTC-C. |  | 9 | 2024-07-18 | TBA for REFURBISHMENT OF JOHN CRANE MAKE DRY GAS SEALS (DGS) INSTALLED IN SIEMENS MAKE HP LEAN GAS COMPRESSOR (LGC) UNITS OF C2C3 PLANT DONE
|  |  | 10 | 2024-07-18 | Team PRAYAAS from Mechanical Department selected as 1st Runner Up for CMD Trophy Award of 2022-23
|  |  | 11 | 2024-07-19 | SOP for GPU and HVJ Station was approved by CGM (O&M-GPU & HVJ)
|  |  | 12 | 2024-07-23 | Procurement of filter elements for Air Intake System of Gas Turbines installed at C2C3 Plant approved and Indent Raised for INR 5.98 CR
|  |  | 13 | 2024-07-24 | VC concluded for water glycol chilling system required for Naphtha vapor recovery during tanker loading.
|  |  | 14 | 2024-07-25 | Release orders for spares and services worth INR 6.05CR for calendar Year 2024 issued against Long-Term Planning (LTP) contract for Lean Gas Compressor package maintenance
|  |  | 15 | 2024-07-26 | Mechanical Departmental Meeting conducted for July 2024.
|  |  | 16 | 2024-07-26 | Procurement of Instrument and Seal Air coolers for Gas Turbines of Lean gas compressor (LGC) units installed at C2C3 Recovery Plant approved and Indent Raised for INR 1.22 CR
|  |  | 17 | 2024-07-26 | FCV installation in VAPL line: Child PO awarded to M./s Lyons for PMC service, site visit done for P&ID, Design basis etc. held on 25.07.24 & 26.07.24
|  |  | 18 | 2024-07-26 | VDPL Vent Recovery as GTG/GTCs fuel: Child PO awarded to M./s Lyons for PMC service, P&ID revision-2 received, design basis received, site visit done for GAD preparation held on 25.07.24 & 26.07.24
|  |  | 19 | 2024-07-27 | Technical discussion done with M/s President Engineering for Anchor Bolts manufacturing and test for Electric Drive Project
|  |  | 20 | 2024-07-27 | Technical discussion done with M/s Aeroflex for Felxible Hose sizes and specifications for Electric Drive Project
|  |  | 21 | 2024-07-27 | Final TBA done for Procurement of Non-sparking tools.
|  |  | 22 | 2024-07-27 | Shipment of M/s Solar Turbines make Titan130S Gas Engine Assembly Serial No. 0081L installed in DVPL-B skid for Overhauling
|  |  | 23 | 2024-07-30 | TBA for Hiring Crane Services (300MT Crane)
|  |  | 24 | 2024-07-30 | Procurement of Regenerator column (16-CC-102) Internals installed in C2C3 Recovery Plant GSU at GAIL Vijaipur approved and Indent Raised for INR 3.8 CR
|  |  | 25 | 2024-07-30 | Kirloskar Ebara Pumps Limited Mr. Rohit Upadhye Sr. Manager –Turbine CSD visited for KEPL steam turbines performance review and O&M effectiveness enhancement possibilities discussion.
|  |  | 26 | 2024-07-30 | BEC TBA Done for 27 Nos bidders for procurement of 02 Inch Gate vlave for utility cooridor work.
|  |  | 27 | 2024-07-31 | Hydrogen capability in SGT 700 presentation by Siemens Energy Sweden team

## Major O&M Jobs
Major O&M Jobs for July 2024
Sr. No. | Section | Very Short Quantitative Description | Photo-1
1 | C2C3 | REPLACEMENT OF COUPLING HUB & YOKE OF ID FAN-2 IN CT-3 DUE TO TRIPING OF ID FAN -2 AT HIGH VIBRATION. COUPLING HUB & YOKE FOUND DAMAGED ON BOTH MOTOR & GEAR BOX SIDE . SO, ACCORDINGLY REPLACED AND ISSUE HAS BEEN RESOLVED.
2 | C2C3 | In DM tank for N2 blanketing, earlier civil sealing pot having length of around approx. 300 mm at site was installed. Metallic drain seal pot fabricated and erected at the place of civil sealing pot to save water due to leakage.
3 | C2C3 | The fabrication and erection of the borewell discharge header from the NFL gate to the Reservoir-II area, the C&P store area to the Reservoir-II area, and watch tower number-3 to the Reservoir-II area, as marked in the following screenshot, have been completed to connect the 13 borewells. Approximately 2 kilometres of the header have been fabricated and erected using scrap pipes from the fire water line header. The header comprises 4-inch, 6-inch, 8-inch, and 10-inch pipes according to the flow requirements.
4 | C2C3 | MOC: site work commencement of 6 inch BOG line, Total -138 Inch-dia has been completed.
5 | C2C3 | MOC: site work commencement of 2 inch fuel gas line. Total-80 Inch-dia has been completed.
6 | C2C3 | MOC: Prefabrication job of 24 Inch GSU bypass line, Total 168 Inch-dia prefabrication work completed.
7 | C2C3 | New ready store development at C2C3 fabrication yard
9 | C2C3 | Blinds/spacers storage racks and hangers fabricated in newly developed ready store at C2C3 fabrication yard.
10 | C2C3 | CT fan blade & water distribution pipe replacement at HVAC Auditorium
11 | C2C3 | FWPH Jockey pump maintenance
12 | C2C3 | ONLINE SEALING OF 14 INCH IV UPSTREAM FLANGE OF LP PRDS VENT LINE
13 | C2C3 | REPLACEMENT OF BEARING ISOLATOR IN TURBINE OF CWP-E .Lube oil leakage is observed from bearing in DE side of steam turbine in Cooling water pump -E installed at CT-3. To eliminate the oil leakage, labyrinth seal is replaced by Bearing isolator. When bearing cover is opened scratch marks and groove is observed on shaft. Bearing liner is also found in damaged condition. So, a new rotor assembly along with bearing isolator is replaced.
14 | C2C3 | REPLACENT OF HCL UNLOADING PUMP IN CT-3. THE CASING OF PUMP IS DAMAGED AND HENCE OTHER MAINTAINED PUMP INSTALLED.
15 | C2C3 | INTERNAL PAINTING OF DM WATER STORAGE TANK-B (32-TT-001B)
16 | C2C3 | REPLACEMENT OF RGC STANDBY LUBE OIL PUMP (18-PA-116) WITH NEW PUMP : The standby lube oil pump of the RGC machine (18-PA-116) was generating lower discharge pressure than its rated value. As a result, during a trip of the main lube oil pump, the RGC machine would also trip because the standby lube oil pump took time to develop pressure, which was below the desired pressure value. To address this issue, the operational standby lube oil pump was replaced with a new pump. After successful installation, a trial run was conducted, and the new pump was found to be operating normally.
17 | LPG | SOFTENER 2 VESSEL ERRECTION AFTER CONSTRUCTION OF NEW FOUNDATION During site visit near Utility Boiler area, various cracks have been observed in the pedestal foundation of the Softener 2 Vessel. Due to these cracks the Vessel began to tilt at an inclination from its upright standing position. It presents a risk of the vessel tipping over in the near future, damaging the adjacent equipment, connected piping and the vessel itself. Therefore, it has been shifted from the damaged pedestal support to carry-out the construction of new pedestal support for the same. After construction of new foundation and its curing period, it has been successfully erected and all associated piping connection completed.
18 | LPG | PROVISION PROVIDED FOR BYPASS LOOP WITH STANDBY STRAINER ARRANGEMENT IN THE EXISTING COOLING WATER SUPPLY LINE AT GREEN H2 BATTERY LIMIT Due to frequent choking of strainer installed in cooling water supply line at Green H2 battery limit, the plant need to be shut-down for the duration of strainer cleaning. This poses the major challenge in continuous running of the Green H2 plant and hence even its PGTR can’t be possible with the existing arrangement. To overcome the issue, it is decided to provide a standby strainer arrangement in parallel to the existing strainer. So a bypass loop is fabricated and installed at the site for the same arrangement.
19 | LPG | To enhance the floating capacity of the algae skimmer by upgrading from a 10-inch PVC ball to a 12-inch PVC ball. The repair work also included cleaning the strainer, replacing the flapper hinges, and modifying the PVC ball.
| LPG | INSPECTION OF PRESSURE VESSELS IN LPG OFFSITES AS PER OISD STD-128 To comply with OISD STD-128, external inspection of the pressure vessels in LPG Offsites is under progress. Inspection of IA receiver (20-V-202), PA receiver (20-V-209), Nitrogen Buffer Vessel (61-V-001), LPG Flare KOD (20-V-207) and LPG Flare Seal Drum (20-V-209) was completed in this month. Various NDT techniques like UTG, MPI, DPT, UFD, etc. was carried out to assess the integrity of equipment and further evaluate Remaining Life of the equipment as per API 579-1 (Fitness for Service).
| LPG | INTERNAL INSPECTION OF HEAT EXCHANGERS IN LPG TRAIN-12 To comply with OISD STD-134, Internal inspection of the heat exchangers tubes was carried out by advanced NDT techniques like Remote Field Electromagnetic Testing (RFET) & Eddy Current Testing (ECT) in LPG Train-12 during this months. Along with ECT & RFET, Phased Array Ultrasonic Testing (PAUT) of weld joints of shell of heat exchangers was also carried to assess the integrity of weld joints of shell. Advanced NDT techniques like ECT & RFET helps in assesing any wall loss/ defects in the tubes of heat exchangers. Based on results of RFET/ECT, preventive measures are taken to ensure reliabilty of the equipment.
HVJ | 1 | Shipment of M/s Solar Turbines make Titan 130S Gas Engine Assembly Serial No. 0081L installed in DVPL-B SKID for overhauling Engine shipped from Vijaipur on 23.07.2024 and received at Mumbai warehouse on 27.07.2024. Air Freight from Mumbai scheduled on 06.08.2024. Scheduled overhauling slot at M/s Solar Facility is Sept’2024 to Dec’2024
HVJ
HVJ
HVJ
HVJ
HVJ
HVJ
HVJ
HVJ
HVJ
HVJ
HVJ
HVJ
HVJ | 2 | Replacement of DVPL EOT Wheels Some abnormal noise noticed during movement of DVPL EOT crane. On Inspection, it has been found that two number of DVPL EOT are damaged (cracks developed on wheel surface). Accordingly, it has been decided to replace damaged EOT wheels with new ones.
HVJ
HVJ
HVJ
HVJ
HVJ
HVJ
HVJ
HVJ
HVJ
HVJ
HVJ
HVJ
HVJ
HVJ
HVJ
HVJ
HVJ
HVJ
HVJ | 3 | Oil spillage from Pneumatic Starter Vent and higher GG lube oil consumption in KO1E An oil spillage was reported from the vent of the pneumatic starter of the K01E KC5 gas engine. Upon checking the drain of the starter vent, a continuous small amount of oil was found flowing out. The oil consumption rate was monitored over several hours, revealing an unusually high consumption of approximately 5 liters overnight. Upon disassembling the starter for a thorough inspection, oil was found in the starter lobes. The starter seal was identified as damaged, which was likely the cause of the oil spillage. After the replacement of starter seal, the machine was restarted to check for abnormalities. No abnormalities detected.
HVJ
HVJ
HVJ
HVJ
HVJ
HVJ
HVJ
HVJ | 4 | DVPL HRSG-C DRUM SAMPLE LINE CHOCKING Steam Drum sample analysis was not possible due to chocking of sample line. Accordingly, for identification of issue, cutting was done multiple bends and critical locations. Afterwards, chocking was found near upstream of isolation valve of Sample analyzer. After cleaning of Sample line, welding has been done. During operation of HRSG, no leakage detected at weld joints and sample collection done.
HVJ
HVJ
HVJ
HVJ
HVJ
HVJ
HVJ
HVJ
HVJ
HVJ
HVJ
HVJ
HVJ
HVJ
HVJ
HVJ
HVJ
HVJ | 5 | Electrification of Gas Turbine drive in Branch line K02A Skid 03 Nos VFD duct-able AC installation, commissioning done in VDPL substation. VDPL substation partition work for HVAC system completed (12.6 m x 3.8m x 3.8m) by ISMC 100 channel: 3.8m height 03 Nos verticals, 03 Nos horizontal of 3.8m channels, and 12.8m -02 Nos. Base plates design (450mm x 500 mm – 08 Nos, 650mm x 500mm -02 Nos) drawings and arrangement plan. Excavation work in-progress on GTG side (19000 x 1200mm) & 02B side (2000 x 1200mm)

## Major POs
Major POs Placed (over 5 Cr.) for July 2024
Sr. No. | Section | Date of PO | Very Short Description

## KS Sessions and Safety Talks
KS Sessions and Safety Talks for July 2024
Sr. No. | Section | Very Short Quantitative Description (include name of contract & No. of persons for Safety talk by EICs) | Photo
1 | C2C3 | Tool Box Talk (TBT) with NDT personnel & Painting workers on Topic - "Confined Space Job & Work at Height jobs" at DM Plant (No. of Workers - 13 nos.)
1 | LPG | Tool Box Talk (TBT) with HYDRO-JETTING team
2 | HVJ | TOOL BOX TALK WITH WORKER OF "AMC M/S JYOTI ENGINEERING " on Topic " Vessel Entry and Work at height Jobs" at HVJ workshop( 14 workers along with GAIL Employees)

## Critical Equipment Availability
Critical Equipment Availability for month - July 2024
Unit | Equipment | Hours Available | % Availability | Remarks | Add in Report - Note: No. of Hours in Month = |  |  |  |  | 744
C2C3 | LGC-A | 737 | 99.06% | Communication Card Failure
| LGC-B | 735 | 98.79% | Communication Card Failure
| LGC-C | 741 | 99.6% | Communication Card Failure
| KE-1 | 744 | 100% | -
| KE-2 | 744 | 100% | -
| PRC | 744 | 100% | -
| RGC | 744 | 100% | -
| STG | 744 | 100% | -
| FD FAN | 744 | 100% | -
LPG | LGC-1 | 744 | 100% | -
| LGC-2 | 744 | 100% | -
| PRC-1 | 744 | 100% | -
| PRC-2 | 744 | 100% | -
| LEF-1 | 744 | 100% | -
| LEF-2 | 744 | 100% | -
| KE-1 | 744 | 100% | -
| KE-2 | 744 | 100% | -
[5 empty] | Unit | Equipment | Hours Available | % Availability | Remarks
[5 empty] | HVJ | GTG-A | 744 | 100% | -
[6 empty] | GTG-B | 744 | 100% | -
[6 empty] | GTC-A (ML) | 744 | 100% | -
[6 empty] | GTC-B (ML) | 744 | 100% | -
[6 empty] | GTC-C (ML) | 744 | 100% | -
[6 empty] | GTC-D (ML) | 744 | 100% | -
[6 empty] | GTC-E (ML) | 744 | 100% | -
[6 empty] | GTC-A (BL) | 0 | 0% | Engine Removed for Electric Drive
[6 empty] | GTC-B (BL) | 744 | 100% | -
[6 empty] | GTC-C (BL) | 744 | 100% | -
[6 empty] | HVJ DEG | 744 | 100% | -
[6 empty] | DVPL GTC-A | 744 | 100% | -
[6 empty] | DVPL GTC-B | 0 | 0% | Engine Removed for Overhauling
[6 empty] | DVPL GTC-C | 744 | 100% | -
[6 empty] | VDPL GTC-A | 744 | 100%
[6 empty] | VDPL GTC-B | 744 | 100% | -
[6 empty] | VDPL GTC-C | 0 | 0% | Engine sent for Overhauling
[6 empty] | VDPL DEG | 744 | 100% | -
[6 empty] | DVPL IAC-A | 744 | 100% | -
[6 empty] | DVPL IAC-B | 744 | 100% | -
[6 empty] | VDPL IAC | 744 | 100%

## Crtical Spares
Plant | No. of Spares
| Adequate Qty (Qty > Min) | Threshold Qty (Qty = Min) | Insufficient Qty (Qty < Min)
C2C3 | 0 | 26 | 7
LPG | 6 | 17 | 5
HVJ | 13 | 26 | 11
List of Insufficient Critical Spares
|  |  |  | PLANT | MATERIAL CODE | DESCRIPTION | STATUS
|  |  |  | C2C3 | 1544010046 | DRY GAS SEAL SET - LGC HP COMP | PO Placed No. 5100004058. Complete Spares materials are expected to be received by Sept. 2024.
[5 empty] | 1537990010 | KE-1 SPARE ROTATING ASSEMBLY | SRA utilized in Shutdown in Apr-2024. Stripping of pulled out SRA done for spares assessment.
[5 empty] | 1191118390 | GAS GENERATOR SGT 700 | Readiness expected by Dec 24 through LTP. Stripping of GG required to ascertain spares requirement for overhauling.
[5 empty] | 1512701350 | DRY GAS SEAL FOR PRC COMPRESSOR | DGS Sent for refurbishment under warranty to vendors work,
[5 empty] | 1125526310 | THRUST BEARING PAD FOR PRC TURBINE | PR Sent (PR No. 20119252) TBA Done. FOA to be placed.
[5 empty] | 1512701360 | JOURNAL BEARING ASS'Y WITH 3-RTD 5PAD/SET of THR END | PR Sent (PR No. 20119252) TBA Done. FOA to be placed.
[5 empty] | 1512701370 | JOURNAL BEARING ASS'Y WITH 3-RTD 5PAD/SET of JNL END | PR Sent (PR No. 20119252) TBA Done. FOA to be placed.
List of Insufficient Critical Spares
|  |  |  | PLANT | MATERIAL CODE | DESCRIPTION | STATUS
|  |  |  | LPG | 1174026110 | LEF GT ROTOR ASSY, L.P | Material Dispatched from vendor. EDD: Aug. 2024
[5 empty] | 1174026500 | LEF GT HP ROTOR ASSY | Material Dispatched from vendor. EDD: Aug. 2024
[5 empty] | 1174023140 | LEF GT TRANSITION PIECE | Material Dispatched from vendor. EDD: Aug. 2024
[5 empty] | 1174025100 | CONVERTER, HYD, TORQUE | 1 Qty. Available at shop floor
[5 empty] | 1155120990 | LGC GT CAP & LINER ASSY | PR Sent (No. 20119667, Dt. 24.04.2024). PO to be placed.(02 Qty from Usar available at workshop.)
|  |  |  | HVJ | 1170101696 | M/L GG BRG,THRUST, | 1 Qty. Available at shop floor
[5 empty] | 1190113696 | M/L GG PUMP HYDRAULIC | 1 Qty. Available at shop floor
[5 empty] | 1190036346 | GTG STARTER,GAS,KB5, | 1 Qty. Available at shop floor
[5 empty] | 1190030203 | GTG PUMP,HYD, | On order stock
[5 empty] | 1190033444 | GTG BRG,RH SHFT,3.5IN DIA | 1 Qty. Available at shop floor
[5 empty] | 1190033454 | GTG BRG,LH SHFT,3.5IN DI | 1 Qty. Available at shop floor
[5 empty] | 1167107336 | PUMP,LO ASSY,EXCLUD CPLG,P/N-1014293-5 | 1 Qty. Available at shop floor
[5 empty] | 1580400203 | CRANK SHAFT,1721MM,P/N 35172090 | 1 Qty. Available at shop floor
[5 empty] | 1569030116 | VDPL GG SHAFT SEAL ASSM,DRY GAS, | 1 Set Sent for refurbishment. EDD: Sept. 2024
[5 empty] | 1168030026 | VDPL POWER TURBINE ROTOR | 02 Nos available with location name 3018 NG Transmission - Noida . Physically at Vijaipur
[5 empty] | 1168030046 | VDPL GT FUEL NOZZLE ASSEMBLY | 2 Set Available at shop floor

## Statutory Compliances
Location | Equip. / Vessel | Governing Standard | Inspected On | Due on | Inspection Status
C2C3 Spheres | A | SMPV (U) Rules 2016 | 2022-11-11 | 2027-11-11 | Completed
| B |  | 2022-12-24 | 2027-12-24 | Completed
| C |  | 2023-02-10 | 2028-02-10 | Completed
LPG Spheres | A |  | 2023-02-25 | 2025-02-25 | Completed
| B |  | 2022-03-16 | 2027-03-16 | Completed
| C |  | 2022-12-27 | 2025-01-04 | Completed
| D |  | 2022-05-11 | 2027-05-11 | Completed
| E |  | 2022-11-03 | 2027-11-03 | Completed
| F |  | 2022-08-03 | 08-08-2024* | Job U/P.
| G |  | 2023-05-10 | 2028-05-11 | Completed
| H |  | 24.02.2018 | 24.02.2023* | Repair to be done.
Propane Spheres | A |  | 2019-11-13 | 2024-11-13 | Completed
| B |  | 2020-02-21 | 2025-02-20 | Completed
| C |  | 2020-03-20 | 2025-03-20 | Completed
Naphtha Tanks | A | OISD 129 | 02.09.2013 | 02.02.2034 | Completed
| B |  | 30.09.2013 | 29.09.2023* | Planned after monsoon
Location | Equip. / Vessel | Governing Standard | Inspected On | Due on | Inspection Status
Pentane Bullets | A | OISD 128 | 2021-01-05 | 2026-01-04 | Completed
| B |  | 2020-12-28 | 2025-12-27 | Completed
| C |  | 2020-12-19 | 2025-12-18 | Completed
| D |  | 2020-09-30 | 2025-09-29 | Completed
| E |  | 2020-09-25 | 2025-09-24 | Completed
N2 Bullets | A | SMPV (U) Rules 2016 | 02.06.2023 | 01.06.2028 | Completed
| B |  | 19.05.2023 | 18.05.2028 | Completed
Utility Boiler |  | IBR | 10.06.2024 | 10.06.2025 | Completed*
C2C3 HRSG Boiler | 1 |  | 13.04.2024 | 13.04.2025 | Completed
| 2 |  | 05.12.2023 | 11.12.2024 | Completed
| 3 |  | 13.04.2024 | 13.04.2025 | Completed
C2C3 HRSG Economiser | 1 |  | 13.04.2024 | 13.04.2026 | Completed
| 2 |  | 12.12.2022 | 11.12.2024 | Completed
| 3 |  | 03.04.2023 | 02.04.2025 | Completed
LPG Pack. Boiler |  |  | 13.04.2024 | 02.04.2025 | Completed
DVPL HRSG | A |  | 20.02.2023 | 19.02.2025 | Completed
| C |  | 08.09.2023 | 08.09.2025 | Completed
Remarks | 1. LPG Sphere F: Inspection job is U/P. 2. LPG Sphere H: Repair Job to be carried out. 3. Naptha Tank B: Inspection is planned after monsoon.

## Budget Utilization (hidden)
PLANT | BUDGET PROVISION |  | TOTAL UTILIZED | % UTILISATION
| RE 23-24 | BE 24-25
C2C3 | 3689 | 3622 | 2124 | 57.58%
LPG | 2546 | 1152 | 1845 | 72.47%
HVJ | 1986 | 2415 | 1596 | 80.36%

## GPU Equipment Overhauling
Sr. No. | Equipment | Running Hours @ End of July | Details of Last Inspection | Next Inspection Due | Inspection Overdue By: (Running Hours)
1 | LPG-11: LGC | 256699 | Combustion Inspection done in March 2023 at 249K R. H. | HGPI due at 262K R. H. | -5301
2 | LPG-12: LGC | 249079 | HGPI done in August 2023 at 243K R. H. | Major Inspection due at 259K R. H. | -9921
3 | LPG-11: PRU-1 | 173110.8233 | HGPI done in April 2022 at 166K R.H. | Major Inspection due at 179K R. H. | -5889.1767
4 | LPG-12: PRU-2 | 172571 | Extended HGPI (MI) done in September 2021 at 165K R. H. | Combustion Inspection due at 179K R. H. | -6429
5 | LPG-11: LEF-1 | 160123 | Combustion Inspection done in September 2023 at 154K | HGPI due at 165K R. H. | -4877
6 | LPG-12: LEF-2 | 150308 | Combustion Inspection done in September 2022 at 143K R. H. | HGPI due at 156K R. H. | -5692
7 | C2C3: LGC - A | 42852 | A-Type Inspection done in April 2024 at 40K R. H. | A-Type Inspection at 52K R. H. | -9148
8 | C2C3: LGC - B | 45414 | A-Type Inspection done in April 2024 at 42K R. H. | A-Type Inspection at 52K R. H. | -6586
9 | C2C3: LGC - C | 48970 | A-Type Inspection done in April 2024 at 46K R. H. | C-Type Inspection at 60K R. H. | -11030
10 | C2C3: PRC | 61221 | Major Overhauling Steam Turbine done in Feb. 2023 at 50K R. H. | Minor Inspection due at 75K R. H. | -13779

## HVJ Engine Status
Equipment | Make | Model | Installed Qty | Spare Qty | Healthy Qty | Overhauling Due for | Under Overhauling | Under Tendering
GAS GENERATOR | ALLISON | 501-KB5 | 8 | 2 | 8 | 2 | 0 | 2
| ALLISON | 501-KC5 | 28 | 5 | 26 | 6 | 1 | 4
| ROLLS-ROYCE | RB211 24G | 8 | 2 | 8 | 0 | 2 | 4
| ROLLS-ROYCE | RB211 24GT DLE | 10 | 0 | 8 | 1 | 1 | 0
| SOLAR TURBINE | TITAN 130S | 3 | 0 | 2 | 0 | 1 | 0
| EGT TORNADO | SGT-200 | 2 | 1 | 2 | 0 | 1 | 0
POWER TURBINE | DRESSER RAND | GT-22C | 28 | 0 | 26 | 2 | 1 | 1
| ROLLS-ROYCE | RT-62 | 8 | 0 | 8 | 0 | 0 | 0
| ROLLS-ROYCE | RT-61 | 10 | 0 | 10 | 0 | 0 | 0
| EGT | SGT-200PT | 2 | 1 | 2 | 0 | 1 | 0
COMPRESSOR | ROLLS-ROYCE | RF3BB36 | 6 | 0 | 6 | 0 | 0 | 0
| ROLLS-ROYCE | RF2BB36 | 4 | 0 | 4 | 0 | 0 | 0
| DRESSER-RAND | CDP-416 | 28 | 0 | 28 | 0 | 0 | 0
| DRESSER RAND | DR452B3 | 2 | 0 | 2 | 0 | 0 | 0
| BHEL | BCL405A | 3 | 0 | 3 | 0 | 0 | 0

## HVJ Engine Overhauling Status
Sr. No | Model | Serial Number | Compressor Station | Last Overhauled in | Status
1 | KB5 | ASP1689 | Jhabua | 2024 | Engine shifted to Vijaipur & received at Vijaipur on 24.05.2024
2 | KB5 | ASP1231 | Auraiya | 2024 | Engine received after overhauling in Auraiya.
3 | KC5 | ASP1822 | Hazira | 2024 | Engine received after overhauling in Hazira on 11.06.2024
4 | KC5 | ASP1208 | Hazira | 2024 | Engine received after overhauling in Hazira on 08.06.2024
5 | KC5 | ASP1981 | Hazira | - | Engine builtup is under progress at vendor's work
6 | KB5 | ASP1860 | Jhabua | 2015 | Tendering stage, Price bid opened.
7 | KB5 | ASP2094 | Auraiya | 2009 | Tendering stage, Price bid opened.
8 | KC5 | ASP1216 | Hazira | 2004 | Tendering stage, Price bid opened.
9 | KC5 | ASP1225 | Hazira | 2010 | Tender floated, bid submission due date is 29.07.2024
10 | KC5 | ASP1980 | Hazira | 2011 | Tender floated, bid submission due date is 29.07.2024
11 | KC5 | ASP1734 | Vijaipur | 2003 | Tender floated, bid submission due date is 29.07.2024
12 | RB211 24GT DLE | 1890-2046 | Vijaipur | - | After overhauling Engine received at Mumbai on 30.07.2024
13 | RB211 24GT DLE | 1890-2048 | Vijaipur | - | Engine to be sent after receipt of 1890-2046
14 | Solar Titan130S | 0082L | Vijaipur | 2024 | Engine installed & comissioned at DVPL GTC-C
15 | Solar Titan130S | 0081L | Vijaipur | 2011 | Engine shipped for overhauling from Vijaipur on 23.07.2024
16 | GT-22C | T-5551 | Auraiya | 2020 | Warranty repair, PT dismantled, warranty claim negotiation is in progress
17 | GT-22C | T-5555 | Vijaipur | - | After negotiation on revised offer, vendor has submitted its response.

## Long Term Jobs
Sr. No. | DESCIRPTION | JOB STATUS | PHOTO
1 | Pre-Feasibility Study for Electrificatin of NG Driven Equipment at GPU Vijaipur | 1. Draft Report submitted by EIL and Queries discussed through meeting. 2. Final Report awaited from M/s EIL.
2 | Installation of GWR LTs in LPG & Propane Spheres | Contract for LPG & Propane Sphere inspection lined up and LOA awarded to M/s TMC, Kolkata. 1. GWR commissioned in LPG Sphere A, B, C, D, E, F, G. Contract for sphere inspection lined up and LOA awarded to M/s TMC. 2. Commissioning of GWR in Propane spheres A, B and modification in Propane sphere C to be done during statutory inspection.
3 | Condition assesment of LPG & Propane Horton Spheres | Reports & Repair procedure for Plate weld received from M/s EIL.For lining up of contract for carrying out repair of LPG Sphere H, quotations are received from prospective bidders. Subsequently, proposal for administrative approval has been moved for lining up of repair contract.
4 | C2C3 & LHC Product Rnhancement | 1. Chiller: TQ reply received from 1 bidder M/s Sumitomo. TQ-2 raise to bidders. 2. Composite works: Proposal already initiated for additional investment approval. 3. Vessels - Delivery expected by Aug’24 4. Valves Delivered against PO: 5700048768. Documentation work under progress..
5 | Guillotine Shutter cum Diverter Damper for Tighter Sealing | Virtual meeting with M/s Thermax conducted on 07.06.2024 for regarding expediting the testing process. Performance Testing at vendors works is planned in August 2024.
Sr. No. | DESCIRPTION | JOB STATUS | PHOTO
6 | Comprehensive Tank Farm Shutdown of LPG Storage area | Valves procurement - Ball valve:- M/s NITON VALVES PRIVATE LIMITED, Ahmedabad. Material partly delivered. PO No. 5700051760 EDD: 30.09.2024
7 | Table Top Study of M/s Siemens | All 03 Sites reports received, review and comments being done.
8 | Flare Tip Refurbishment | Request mail sent for budgetary quotation. Quotation received from 01 vendor. Quoation from 02 vendors is pending.
9 | Borewell Piping Layout | Approx. 1.7 km pipeline laying done at site. Primer applied on pipeline. Painting to be carried out.
10 | CBD Project | 1.Pumps, PO: 5800005468 Placed to M/s KSB, CDD: 04.08.2024, QAP approved, detailed engineering completed, GA drawing approved on 19.07.2024. 2.CBD vessel, PO : 5700051457 placed to M/s Udkam Process Equipments,Drawing & QAP approved, EDD - Sept 2024 3.For composite works : Price part recieved from EIL for estimate preparation. Query from Mechanical resolved, Query from Electrical & Instrument is under assesment by EIL, reply of EIL on query is awaited.
11 | Siemens LTP for SGT -700 | Meeting with M/s Siemens done on 03-06-2024 regd. issues with LTP. Followup meeting to be planned in August 2024.
12 | C2C3 LGC-A Pulled out GG Readiness | Activity list for dismantling of pulled out GG is ready. Spares requirement for refurbishment to be made after GG stripping.
Sr. No. | DESCIRPTION | JOB STATUS | PHOTO
13 | C2C3 KE-1 SRA Refurbishment | Budgetary quotoation received from vendor in which quoted prices are very high. Discussion for review of prices is under progress.
14 | Expander Compressor After Cooler Procurement | 1) 11-E-109 i) PO placed, LOA: 5700052564 Dated : 21.03.2024, CDD : 08.11.2024 ii) QAP approved on 29.05.2024 and drawings approved on 05.06.2024. iii) Progress Report seeked from Vender by E-mail communication on 31.07.2024. 2) 11-E-108 INTER COOLER Admin. approval done, PR (20121873, Dated 24.07.2024) raised.
15 | FR-3 Exhaust Revamping | PO: 5300039015 placed to M/s BGGTS on 16.06.2023 with CDD 15.06.2025 i) Vendor's Site visit (for duct measurement) conducted in May 2024 ii) Silencer duct received at site in June 2024, EDD for balance materials Aug 2024.
16 | FR-3 GT (Usar) Rotor & HGP Component Refurbishment | Budgetary quotation received from OEM. Price negotiation and scope of work finalization u/p with OEM.
17 | Services for Failure Mode Analysis | Administrative approval has been taken for lining up of contract on QCBS basis for Failure Investigation & RCA of Mechanical Components on proposal approved on 30.07.2024. Nomination of Technical Committee is under progress for finalizing QCBS technical criteria.

## Asset Integrity
S No. | Standard | Description | Status & Photo |  | Photo
1 | OISD-STD-128 | NDT & Pneumatic Testing of PSA N2 Surge Vessels-A/B/C in IA/IG Plant | Jan 2024 - Completed
2 | OISD-STD-130 | Visual, UTG & LRUT of Feed Gas & Lean Gas lines, RLNG line, Amine Loop | Jan 2024 - Completed
3 | OISD-STD-128 | NDT of LP Air Receiver and HP Air Receiver in IA/IG Plant | Feb 2024 - Completed
4 | OISD-STD-128 | Comprehensive NDT Inspection of Pr. Vessel - Side Stream Filter (25-GN-001 A/B) | Mar 2024 - Completed
5 | OISD-STD-128 & OISD-STD-130 | Statutory Inspection of Process Pipelines, Pressure vessels & Lifting Tools | Apr 2024 - Completed
1 | OISD STD-128 | Comprehensive NDT Inspection of Pr. Vessels - Water Seal Drum (63-VV-003), Deaerator (34-VV-002) | Apr 2024 - Completed
1 | OISD STD-134 | NDT Inspection of 34 No.s Air Fin Coolers at C2C3 Plant | Apr 2024 - Completed
1 | OISD STD-134 | NDT Inspection of 51 No.s Heat Exchangers at C2C3 Plant using ECT, RFT & PAUT Techniques . | Apr 2024 - Completed
2 | OISD STD-128 | Advanced NDT Inspection of 24 No.s Pr. Vessels & Columns using UTG & PECT – External & Internally | Apr 2024 - Completed
3 | OISD STD-128 | Scanning of Dryer Lines near MOVs by PECT Technique at 13 Locations | Apr 2024 - Completed
4 | OISD STD-130 | LRUT of Approx. 3925 m Process Piping at C2C3 Unit Area | Apr 2024 - Completed
5 | OISD STD-133 | Inspection of All 48 No.s Regeneration Gas (RG) Heater Tubes (Tag No.. 18-FF-101) | Apr 2024 - Completed
S No. | Standard | Description | Status | Photo | Photo
6 | MP Factories Rules 1962 & OISD STD-129 | Inspection & Internal Painting of Spent Amine Tank using UTG - External & Internally | Apr 2024 - Completed
7 | OISD STD-130 | LRUT/ SRUT of Approx. 2700 m Process Pining at LPG Unit Area | May 2024 - Completed
8 | OISD STD-129 | NDT Inspection of DM Water Tank - B at C2C3 DM Plant (External) | June 2024 - Completed
9 | OISD STD-128 | Inspection & RLA of N2 buffer vessel, IA receiver vessel, PA receiver vessel in LPG Offsites | June 2024 - Completed
10 | OISD STD 134 | Internal Inspection of Heat Exchangers in LPG Train-12 | July 2024 - Completed
| OISD-STD-128 | NDT Inspection of 9 nos. Pressure Vessels at C2C3 DM Plant - [External VI, UTG, DPT, MPT, UFD¦ | July 2024 - Completed
| OISD-STD-128 | NDT Inspection of 4 nos. Pressure Vessels at C2C3 DM Plant (External) | July 2024 - Under Progress
| OISD-STD-129 | NDT Inspection of DM Water Storage Tank - B at C2C3 DM Plant (Internal) [UTG of Bottom Plate, VBT, MFL and Internal Painting] | July 2024 - Under Progress
| OISD STD 128 | INSPECTION OF PRESSURE VESSELS IN LPG OFFSITES AS PER OISD STD-128 | July 2024 - Completed
| OISD STD 134 | INTERNAL INSPECTION OF HEAT EXCHANGERS IN LPG TRAIN-12 | July 2024 - Completed

## SAMOC (hidden)
MOC NO. | DESCRIPTION | JOB STATUS | PHOTO | Kindly provide job status in very short/ brief manner. And attach single photo in respective row
1261 | M/L AND B/L VENT LINE SHIFTING | 1. Painting work completed and site clerance done. Lines handover to operation for further use. 2. Followed with operation department for closing of MOC in system.
991 | FUEL GAS FROM RLNG TO MP FOR VDPL COMPRESSORS | 1. Approx. 450 Meter Pipes laying done 2. 100 Joints Welding done. 3. 100% RT done 4. Hydrotest carried out at 138 Kg/cm2 5. Project Commissioned 6. MOC closed from execution end with all related documents uploaded.
2561 | Supply of RLNG from DVPL-I to NFL Vijaip | 1. Tender floated 2. RFQ done 3. TBA Done 4. LOA awarded 5. IRN received for fittings and pipes PR Clubbed with MOC 2561 i.e. Supply of RLNG from DVPL-I to NFL VIJAIPUR. Materials have been received at the site, and pre-fabrication has commenced. To execute the job, NFL shutdown is required. Same has been informed to intending department.
MOC NO. | DESCRIPTION | JOB STATUS
2807 | Utility Corridor for HVJ compressor station | 1. Tender floated 2. RFQ done 3. TBA Done 4. LOA awarded PR Clubbed with MOC 2561 i.e. Supply of RLNG from DVPL-I to NFL VIJAIPUR. A. Material received at site: Pipes & fittings B. 02 inch gate valve TBA done, material will be available in Dec 2024-Jan 2025.
1385 | IA HOOK UP FROM GPU TO HVJ CS | Completed & commissioned. Below activity carried out: 02 Inch line hook-up to dryer inlet. Required NRVs, Valves & Gauge installed Commissioned with mesh strainer with inspection
1262 | BYPASS LINE FOR HP-MP PCV OF NFL LINE | Completed & Commissioned on 08.05.2023. Below activity carried out in NFL PCV skid modification. 1. Modification of PCVs skid 2. Hook-up with existing headers 3. RT test of all joints -25 Joints 4. Hydrotest of complete loop – 138 Kg/cm2 5. Cardboard blasting of total loop – Blasting done in 02 loops till satisfactory parameters 6. 02 Nos PCVs installation. 7. Painting of skid & pipes – Primer & 02 coat paint applied 8. Final De-Blinding – Leak test done after nitrogen purging 9. Commissioning done with HP gas entry. No leak found.
MOC NO. | DESCRIPTION | JOB STATUS
1413 | HOOK-UP OF PLANT AIR FROM GPU TO HVJ | Completed & commissioned. Below activity carried out: 06 Inch line hook-up to discharge header. Required NRVs, Valves, Flow Orifice, Gauge installed Commissioned with mesh strainer with inspection.
2254 | PROVIDING BYPASS FOR AV6118 | Project kept on Hold by Chair Person CGM(O&M)
671 | HP-MAIN LINE CONNECTIONS | Project kept on Hold by Chair Person CGM(O&M)
1824 | REMOVAL OF 14”UNFILTERED RLNG LINE | Completed and Handover to operation
2226 | MODIFICATION FOR VAPL PIPELINE CONNECTION | Job carried out by construction team
| FCV INSTALLATION IN VAPL LINE | Site visit done by M/s LEPL PMC , required reports preparation is in progress.
| VDPL VENT RECOVARY TO GTGS FUEL | 1. PMC services hired. 2. P&ID revsion-1 received and found as per requirement. 3. HAZOP Study to be done

## MOC Jobs
MOC NO. | DESCRIPTION | JOB STATUS
1261 | M/L and B/L Vent Line Shifting | 1. Painting work completed and site clerance done. Lines handover to operation for further use. 2. Followed with operation department for closing of MOC in system.
991 | FUEL GAS FROM RLNG TO MP FOR VDPL COMPRESSORS | 1. Approx. 450 Meter Pipes laying done 2. 100 Joints Welding done. 3. 100% RT done 4. Hydrotest carried out at 138 Kg/cm2 5. Project Commissioned 6. MOC closed from execution side
2561 | Supply of RLNG from DVPL-I to NFL Vijaip | 1. Tender floated; 2. RFQ done; 3. TBA Done; 4. LOA No -5700052935 dated 09.05.2024 awarded, 5. Inspection Release note received for fittings and pipes 6. PR Clubbed with MOC 2807 i.e. Utility Corridor for HVJ compressor station 7. Materials have been received at the site, and pre-fabrication has commenced. To execute the job, NFL shutdown is required. Same has been informed to intending department.
2807 | Utility Corridor for HVJ compressor station | 1. Tender floated; 2. RFQ done; 3. TBA Done; 4. LOA 5700052936 dated 09.05.2024 awarded, 5. PR Clubbed with MOC 2561 i.e. Supply of RLNG from DVPL-I to NFL VIJAIPUR A. Material received at site: Pipes & fittings B. 02 inch gate valve TBA done, material will be available in Dec-Jan 2024-25.
1385 | IA HOOK UP FROM GPU TO HVJ CS | Completed & commissioned. Below activity carried out: 02 Inch line hook-up to dryer inlet. Required NRVs, Valves & Gauge installed Commissioned with mesh strainer with inspection
1262 | BYPASS LINE FOR HP-MP PCV OF NFL LINE | Completed & Commissioned on 08.05.2023. Below activity carried out in NFL PCV skid modification. 1. Modification of PCVs skid 2. Hook-up with existing headers 3. RT test of all joints -25 Joints 4. Hydrotest of complete loop – 138 Kg/cm2 5. Cardboard blasting of total loop – Blasting done in 02 loops till satisfactory parameters 6. 02 Nos PCVs installation. 7. Painting of skid & pipes – Primer & 02 coat paint applied 8. Final De-Blinding – Leak test done after nitrogen purging 9. Commissioning done with HP gas entry. No leak found.
1413 | HOOK-UP OF PLANT AIR FROM GPU TO HVJ | Completed & commissioned. Below activity carried out: 06 Inch line hook-up to discharge header. Required NRVs, Valves, Flow Orifice, Gauge installed Commissioned with mesh strainer with inspection.
2254 | Providing Bypass for AV6118 | Project kept on Hold.
671 | HP-Main Line Connections | Project kept on Hold. Closure under progress by concern department
1824 | REMOVAL OF 14”UNFILTERED RLNG LINE | Completed and Handover to operation
2226 | Modification for VAPL Pipeline Connections | Job carried out by construction team
1385 | IA HOOK UP FROM GPU TO HVJ CS | Completed & commissioned. 02 Inch line hook-up to dryer inlet. Required NRVs, Valves & Gauge installed Commissioned with mesh strainer with inspection
| VDPL vent Recovery to GTGS Fuel | Child PO awarded, site visit done, P&ID under-preparation revision-2 with GAD and isomatric
| FCV Installation in VAPL Line | Child PO awarded, site a done, P&ID under-preparation.
| LP Fuel Gas to HRSG Burner | Job Completed
| 4 inch FGRU to Fuel Gas Interconnection | Job Completed
MOC NO. | DESCRIPTION | JOB STATUS
1231 | 6" Line from SEP-2 to CC-102 Feed line | Job Completed
1402 | Interconnection between 12-VV-110 & 18-VV-116 | Material received, elbows are under TPI stage. Job will be commenced through MOC contract. All material received, job under progress at site.
1735 | Provision of isolation valve in process side of C2C3 Re-boiler (18-EE-114) | Material PO placed. Expected delivery Sept 2024.
1736 | Increasing 18-EE-103 FG B/P Line Size | 24 inch by-pass line Job already completed. Control valve with manual gate valves will be installed during next plant shutdown.
1852 | Modification of CT2 & CT3 CW Interconnection | Request for budgetary quote forwarded. File will be initiated soon.
1981 | Interconnection of C2C3 BOG to LEF | Material received. Line fabrication & erection near battery limit is under progress.
2175 | MOC for CPU ACF Backwash Process | Job Completed
2292 | Laying LP steam header from LPG for HVAC | Design job completed. File will be initiated in Aug 2024 month.
2643 | Laying new 24-inch line from GSU Coalescer filter (16-GN-104) Outlet to GPU Suction KOD (18-VV-101) | Tapping job completed. Fittings received. Piping delivery expected: July'24 1st week. Check valve : Material Received. 24 inch gate valves : EDD: Sept'24 04 nos. 45 degree elbow PATA , STO done. Expected delivery by 20th Aug 2024.
1824 | REMOVAL OF 14”UNFILTERED RLNG LINE | Completed and Handover to operation.
| 16-inch by-pass for propane chiller 18-EE-105 | Material PO placed. Pipe and fittings : Material Delivered. Valves : Sept'24. Vibration issue in inlet header, to be taken help from EIL.

## R&D Projects
SR NO. | DESCIRPTION | JOB STATUS | PHOTO | Kindly provide job status in very short/ brief manner. And attach single photo in respective row
1 | Updation/ Retrofit of Wet Seal to Dry Gas Seal in Dressor Rand Make CDP 416 Compressor | Job is on hold by the competent authority as it is not economically feasible.
2 | Electrical Motor Drive (Prime Mover) for HVJ Compressor Package (One machine in Branch Line) | 1. GEAR-BOX & MOTOR DISPATCHED FROM OEM FACILITY. 2. VFD panel & HT Panel installed at site. 3.Site dismantling and foundation work in-progress. 4.All technical documents approved and cleared for manufacturing
3 | Detailed engineering, design, manufacturing, supply, installation & commissioning of new diverter damper and guillotine shutter wall in Lean Gas Compressor (LGC) at C2C3 Recovery Plant | Virtual meeting with M/s Thermax conducted on 07.06.2024 for regarding expediting the testing process. Performance Testing at vendors works is planned in August 2024.
4 | Installation of FCV in VAPL in order to maintain hydraulics of VAPL & JHBDPL network without compromising lean gas evacuation | Child PO awarded, site visit done, P&ID under-preparation.

## Difficulties Faced
SR NO. | DESCIRPTION OF DIFFICULTY
1
2
3
4
5
6
7
8