## MAIN
GAIL (India) Limited (A Government of India Undertaking - A Maharatna Company)
MECHANICAL DEPARTMENT, VIJAIPUR
MONTHLY PERFORMANCE REPORT JUNE 2024
MAINTENANCE COMPLIANCE
Planned Preventive Maintenance (PM02
| Plant | PLANNED | EXECUTED
| C2C3 | 38 | 38
| LPG | 39 | 39
| HVJ | 37 | 37
Un-planned Maintenance
| Plant | PLANNED | EXECUTED
| C2C3 | 89 | 89
| LPG | 102 | 102
| HVJ | 33 | 33
Breakdown Maintenance
| Plant | No. of Breakdown Jobs carried out | Short Description of Job
| C2C3 | 0
| LPG | 0
| HVJ | 0
0
Jobs Hold for Shutdown
| Plant | No. of Jobs hold | Description
| C2C3 | 0
| LPG | 1 | LGC-1 GT Bearing No. 4 Oil Leakage to be attended
| HVJ | 0
1
VIBRATION MONITORING
| Plant | No. of Equipment Scheduled | No. of Equipment Monitored (Executed)
| C2C3 | 199 | 195 | 1 M/c under standby
| LPG | 235 | 229 | 2 M/c under shutdown as per operational requirement
| HVJ | 71 | 67 | 1.K01E GAS TURBINE STANDBY, K01E COMPRESSOR STANDBY, DVPL IA COMP RADIATOR FAN-2 MAINTENANCE, VDPL GTC-A LOC-2 MOTOR MAINTENANCE
|  | No. of Euipment With Normal Health | Health Index
| C2C3 | 194 | 99.49%
| LPG | 228 | 99.56%
| HVJ | 65 | 97.01%
|  | No. of Equipment With Critical Health | Critical Index
| C2C3 | 1 | 0.5128%
| LPG | 1 | 0.4367%
| HVJ | 2 | 2.985%
|  | Corrective Actions Initiated | Corrective Actions Pending
| C2C3 | 1 | 0 | DEGASSED AIR BLOWER-A Alignment corrected
| LPG | 1 | 0
| HVJ | 2 | 0 | DVPL GTC-C FAN 2 & DVPL GTC-C FAN 6 - Belt tension adjusted and alignment corrected.
LUBE OIL ANALYSIS
| Plant | No. Scheduled for analysis | No. of Samples Analysed
| C2C3 | 21 | 21
| LPG | 8 | 8
| HVJ | 29 | 29
|  | Corrective Actions Required | Corrective Actions Taken
| C2C3 | 0 | 0
| LPG | 0 | 0
| HVJ | 2 | 2 | 1.HVJ DEG marginal moisture contamination.Centrifuge was run to remove moisture & then, resampling was done in GAIL laboratory and moisture content found to be within range 2..VDPL DEG marginal moisture contamination.Centrifuge was run to remove moisture & then, resampling was done in GAIL laboratory and moisture content found to be within range
SPARES MANAGMENT
| Plant | Indents Scheduled for Review | No. of PR Raised | Cumul. No. of Indents Scheduled for Review till this month in F.Y. 24-25 | Cumul. No. of PR Raised till this month in F.Y. 24-25
| C2C3 | 12 | 2 | 19 | 3
| LPG | 9 | 2 | 11 | 6
| HVJ | 2 | 0 | 6 | 3
New Contracts
|  | No. of SR Raised | Cumul. No. of SR Raised till this month in F.Y. 24-25 | Cumul. No. of PO placed till this month in F.Y. 24-25
| C2C3 | 2 | 5 | 1
| LPG | 0 | 2 | 0
| HVJ | 0 | 0 | 0
Running Contracts
|  | Total Current Running Contracts | Contracts requiring Renewal (in next six months) | Contracts Expiring in this month (not requiring renewal)
| C2C3 | 48 | 7 | 2
| LPG | 33 | 6 | 2
| HVJ | 25 | 3 | 0
Manpower Contracts
|  | No. of Contracts | Contracts with valid Workers Insurance
| C2C3 | 7 | 7 | AMC, Crane, Painting, NDT, Fabrication, Insulation, HVAC
| LPG | 2 | 2 | AMC
| HVJ | 4 | 4 | AMC, Fabrication, Insulation, HVAC
Health Monitoring of Contracts (Quarterly)
|  | No. of Contracts | Contracts with Issues
| C2C3 | 3 | 0 | AMC, Painting, Crane,
| LPG | 2 | 0 | AMC, Painting
| HVJ | 5 | 0
Closed Contracts (Quaterly)
|  | No. of Contracts completed as per Schedule | Contracts with Final Bill Cleared | Contracts Closed in SAP
| C2C3 | 3 | 2 | 0
| LPG | 3 | 2 | 0
| HVJ | 2 | 0 | 0
IMS COMPLIANCE
| Plant | No. of Observation | Complied | Pending
| C2C3 | 0 | 0 | 0
| LPG | 0 | 0 | 0
| HVJ | 0 | 0 | 0
|  | 0 |  | 0
AUDIT COMPLIANCE
| Audit Description | Plant | No. of Observation | Complied | Pending
| Internal Safety Audit PNGRB | 5020 | 4 | 4 | 0
| Technical Audit | 5020 | 3 | 3 | 0
| Ext. Sustainability Audit | 5020, 6020, 3015 | 1 | 1 | 0
| Internal Safety Audit PNGRB | 6020 | 4 | 4 | 0
0
GATE PASS DETAILS
|  | New Gate Pass Created | Gate Pass open till last month | Gate Pass Closed in this month | Total current open Gate Pass
| C2C3 | 1 | 3 | 1 | 3
| LPG | 2 | 8 | 0 | 10
| HVJ | 0 | 9 | 1 | 8
E-FILE STATS
|  | No. of e-Files Initiated | No. of e-Files Approved | No. of e-Files Closed
| C2C3 | 9 | 6 | 6
| LPG | 2 | 1 | 1
| HVJ | 1 | 1 | 2
INVOICING COMPLIANCE
| Plant | No. of Invoice Received | No. of Invoice Processed
| C2C3 | 13 | 13
| LPG | 4 | 4
| HVJ | 4 | 3
SAFETY COMPLIANCE
| Plant | Near Miss |  | Safety Observations
|  | Allotted | Reported | Allotted | Reported
| C2C3 | 1 | 1 | 2 | 4
| LPG | 0 | 0 | 3 | 3
| HVJ | 1 | 1 | 2 | 2
LUBE OIL CONSUMPTION
|  | Lube Oil Name | C2C3 Consumption (Ltrs.) | C2C3 Fresh Issued from Store (Ltrs.)
| C2C3 | SP 46 G | 210 | 0
|  | SP 32 | 5 | 0
|  | SP 68 | 20 | 0
|  | 15W40 | 5 | 0
|  | SS 46 | 145 | 210
|  | SS 150 | 25 | 0
| LPG | SERVO PRIME 32T | 0 | 0
|  | SERVO PRIME 68 | 210 | 0
|  | SERVO SYSTEM 68 | 75 | 0
|  | SERVO MESH SP 320 | 10 | 0
|  | SERVO PRESS 68 | 60 | 0
|  | SERVO GEAR HP 140 | 5 | 0
|  | Servo trans fluid A | 20 | 0
|  | SERVO SYSTEM 46 | 5 | 0
|  | SERVO System HLP68 | 35 | 210
|  | SERVO FRIZ 68 | 10 | 0
|  | SERVOS PREMIUM CF 4 15W/40 | 30 | 0
| HVJ | Mobilejet-2 | 210 | 0
|  | Tribunol 46 | 100 | 0
|  | EP 32 | 100 | 0
HAZARDOUS WASTE HADED OVER IN JANUARY
| Plant | Item Description | Weight (kg) | Total Weight (kg)
| C2C3 | Metal | 460 | 1920
|  | Non -Metal | 1460
|  | Lube Oil 2730 Ltr | 0 |  |  | C2C3 | 1920
| LPG | Metal - MS | 1090 | 1190 |  | LPG | 1190
|  | Non Metal - Plastic | 100 |  |  | HVJ | 430
| HVJ | Cotton Waste | 430 | 430
DEPARTMENT MEETINGS
| MONTH |  | DATE OF MEETING
| JAN | 1 | 16.01.2024 |  |  | Approved (IN Lacs) |  | Utilisation (in Lacs)
| FEB | 1 | 0 |  |  | RE-2023-24 | BE 2024-25 | 2024-06-01 | Cumulative - F.Y. 2024-25 | For S&S filter plant then PO then date
| MAR | 1 | 0 |  | C2C3 - R&M | 605.6 | 528.65 | 211.61 | 439.7 | For R&M filter CPF & delete CPF then plant then date
| APR | 1 | 0 |  | C2C3 - S&S | 456.3 | 505.6 | 19.09 | 28.1379
| MAY | 1 | 02.05.2023 |  | C2C3 - CAPEX (O&M) | 2594 | 1263 | 67.76 | 730.8588
| JUN | 1 | 0 |  | LPG - R&M | 305.6 | 324.98 | 70.64 | 74.8379
| JUL | 1 | 07.07.2023 |  | LPG - S&S | 337.5 | 331.2 | 16.47 | 35.796
| AUG | 1 | 0 |  | LPG - CAPEX (O&M) | 6185 | 8153 | 28.71 | 1327.5362
| SEP | 1 | 22.09.2023 |  | HVJ - R&M | 135.45 | 137.37 | 48.03 | 49.7852
| OCT | 1 | 0 |  | HVJ - S&S | 183.72 | 250.38 | 21.85 | 24.2501
| NOV | 1 | 0 |  | HVJ - CAPEX (O&M) | 7946 | 13082 | 0 | 405.1498
| DEC | 1 | 0
| Knowledge Sharing Sessions Details |  |  | Safety talks by EIC
| Plant | No. of session is this month |  | Plant | No. of safety talks conducted in this month
| C2C3 | 0 |  | C2C3 | 1
| LPG | 0 |  | LPG | 1
| HVJ | 0 |  | HVJ | 0
EDMS
| RTI Queries |  |  | Plant | No. of files EDMS Done
| Queries In this month | 1 |  | C2C3 | 0
| Replies Given in this month | 1 |  | LPG | 0
| Total Rreplies given in F.Y. 24-25 | 1 |  | HVJ | 0
LUBE OIL CONSUMPTION
|  | Lube Oil Name | C2C3 Consumption (Ltrs.) | C2C3 Fresh Issued from Store (Ltrs.)
|  | SP 46 G | 210 | 0
|  | SP 32 | 5 | 0
|  | SP 68 | 230 | 0
|  | 15W40 | 35 | 210
|  | SS 46 | 150 | 0
|  | SS 150 | 25 | 0
|  | Mobilejet-2 | 210 | 0
|  | Tribunol 46 | 100 | 0
|  | EP 32 | 100 | 0
|  | SS 68 | 75 | 0
|  | Servo Mesh SP 320 | 10 | 0
|  | Servo Press 68 | 60 | 0
|  | Servo Torque 10 | 5 | 0
|  | Servo Trans Fluid A | 20 | 0
|  | SERVO GEAR HP 140 | 5 | 0
|  | SS HLP68 | 35 | 210
|  | Servo FRIZ 68 | 10 | 0

## PLOTS
|  | 0 | Breakdown Maintenance
|  | 1 | Jobs in This Month Hold for Shutdown
0 | IMS Audit Observations
0 | Audit Points Compliance Pendine
This chart isn't available in your version of Excel. Editing this shape or saving this workbook into a different file format will permanently break the chart.
No. of Orders
No. of Orders
No. of
Corrective Actions
This chart isn't available in your version of Excel. Editing this shape or saving this workbook into a different file format will permanently break the chart.
5
MEETINGS
CONDUCTED
MEETING
DATES
16.01.2024
07.03.2024
28.04.2024
01.06.2024 26.06.2024
CONDUCTED
NOT CONDUCTED

## Major Highlights
Major Highlights for June 2024
Date | Description | NOTE: Add short descriptions of Major Meetings, Presentations, Awards, Engine testings, etc.
2024-06-03 | Virtual Meeting with KPMG on Maintenance System
2024-06-04 | Virtual Meeting with EIC & PESO for hiring of approved agency for Sphere H
2024-06-07 | Virtual Meeting with M/s Thermax was done regd. Guillotine Shutter cum Diverter Damper
2024-06-11 | Virtual Meeting with M/s Siemens on Energy Shop
2024-06-12 | Approx. 1.7 Km piping laying completed for Borewell Header Connection
2024-06-18 | Kick Off Meeting for site activity related to B/L A modification multi disciplinary action carried out at
2024-06-20 | Virtual Meeting with M/s Siemens LTP Team regd. high vibration of LGC-A GT.
2024-06-21 | Virtual Meeting with PESO on repair of LPG Sphere H
2024-06-26 | Meeting with M/s Siemens on GG Swapping
| Meeting with Flender, Siemns for Gear-Box, Main LuBE Oil Pump technical discussion | 03.06.2024
| Meeting with Siemens & Instrument team for automation system configeration for electric drive project | 24.06.2024
| Site meeting & VCs for foundation drawing & design with PMC for elctric drive new foundation work | 08.06.2024
| Meeting with Lyons, Operation, instrument team for VDPL Vent recovery shecme. | 25.06.2024
| Meeting with M/s Siemens for electrification feasibilty at HAZRIA , AURAIYA and VIJAIPUR site | 10.06.2024
29.06.2024 | Presentation with Director Project, OIC Vijaipur and HOD Mechanical for Feasibility of Electrification for 08 Nos compressor stations | 01.06.2024
|  |  | 1 | 2024-06-01 | Presentation with Dir (Project), ED (O&M-CR) and HOD (Mech) for Feasibility of Electrification for Comp. Stations.
|  |  | 2 | 2024-06-03 | Online Meeting with M/s Siemens Energy LTP team for discussion of various pending Issues of LTP and planning of C type Inspection
|  |  | 3 | 2024-06-03 | Price Negotiation Meeting with M/s BGGTS,
|  |  | 4 | 2024-06-03 | Virtual Meeting with KPMG on Maintenance Management System
|  |  | 5 | 2024-06-05 | Virtual Meeting on Repair job of LPG Horton Sphere H with EIL & PESO
|  |  | 6 | 2024-06-07 | Discussion with M/s Thermax for Diverter Damper & Guillotine Damper project progress review through MS team.
|  |  | 7 | 2024-06-08 | Site meeting & VCs for foundation drawing & design with PMC for elctric drive new foundation work.
|  |  | 8 | 2024-06-11 | Meeting with M/s Siemens for electrification feasibilty at HAZRIA , AURAIYA and VIJAIPUR site
|  |  | 9 | 2024-06-12 | Approx. 1.7 Km piping laying completed for Borewell Header Connection
|  |  | 10 | 2024-06-14 | Online technical discussion and demo of M/s Siemens Energy Shop for LGC GT
|  |  | 11 | 2024-06-17 | SSLNG review meeting with M/s MECON, INOX
|  |  | 12 | 2024-06-21 | Online technical discussion with M/s Siemens Product Technical Team regarding High Vibration in LGC-A GT
|  |  | 13 | 2024-06-21 | Virtual Meeting with PESO on repair of LPG Sphere H
|  |  | 14 | 2024-06-24 | Meeting with Siemens & Instrument team for automation system configeration for electric drive project
|  |  | 15 | 2024-06-25 | Meeting with Lyons, Operation, instrument team for VDPL Vent recovery scheme.
|  |  | 16 | 2024-06-26 | Technical discussion on pump length for blowdown systems with KSB
|  |  | 17 | 2024-06-26 | Meeting with M/s Siemens on GG Swapping
|  |  | 18 | 2024-06-26 | Mechanical Department Meeting conducted for June 2024.
12
13
14
15
16
17

## Critical Equipment Availability
Unit | Equipment | Hours Available | % Availability* | Remarks | 720 |  |  |  |  | Unit | Equipment Name | Hours in Month | Hours Available | % Availability | Comments for Lower Availability
C2C3 | LGC-A | 720 | 100% | [6 empty] | C2C3 | LEAN GAS COMPRESSOR -A | 720 | 720 | 100% | -
| LGC-B | 720 | 100% | [7 empty] | LEAN GAS COMPRESSOR -B | 720 | 720 | 100% | -
| LGC-C | 720 | 100% | - | [6 empty] | LEAN GAS COMPRESSOR -C | 720 | 720 | 100% | -
| KE-1 | 720 | 100% | - | [6 empty] | EXPANDER COMPRESSOR -1 | 720 | 720 | 100% | -
| KE-2 | 720 | 100% | - | [6 empty] | EXPANDER COMPRESSOR -2 | 720 | 720 | 100% | -
| PRC | 720 | 100% | - | [6 empty] | PROPANE REFRIGERATION COMPRESSOR | 720 | 720 | 100% | -
| RGC | 720 | 100% | - | [6 empty] | R G COMPRESSOR | 720 | 720 | 100% | -
| STG | 720 | 100% | - | [6 empty] | STEAM TURBINE GENERATOR | 720 | 720 | 100% | -
| FD FAN | 720 | 100% | - | [6 empty] | FD FAN | 720 | 720 | 100% | -
LPG | LGC-1 | 720 | 100% | - | [5 empty] | LPG | LEAN GAS COMPRESSOR - PH-1 | 720 | 720 | 100% | -
| LGC-2 | 720 | 100% | - | [6 empty] | LEAN GAS COMPRESSOR - PH-2 | 720 | 720 | 100% | -
| PRC-1 | 720 | 100% | - | [6 empty] | C3R COMPRESSOR -PH-1 | 720 | 720 | 100% | -
| PRC-2 | 720 | 100% | - | [6 empty] | C3R COMPRESSOR -PH-2 | 720 | 720 | 100% | -
| LEF-1 | 720 | 100% | - | [6 empty] | LEF COMPRESSOR -PH-1 | 720 | 720 | 100% | -
| LEF-2 | 720 | 100% | - | [6 empty] | LEF COMPRESSOR -PH-2 | 720 | 720 | 100% | -
| KE-1 | 720 | 100% | - | [6 empty] | EXPANDER COMPRESSOR - PH-1 | 720 | 720 | 100% | -
| KE-2 | 720 | 100% | - | [6 empty] | EXPANDER COMPRESSOR - PH-2 | 720 | 720 | 100% | -
[5 empty] | Unit | Equipment | Hours Available | % Availability* | Remarks | Unit | Equipment Name | Hours in Month | Hours Available | % Availability | Comments for Lower Availability
[5 empty] | HVJ | GTG-A | 720 | 100% | - | HVJ | GAS TURBINE GENERATOR- A | 720 | 720 | 100% | -
[6 empty] | GTG-B | 720 | 100% | - |  | GAS TURBINE GENERATOR-B | 720 | 720 | 100% | -
[6 empty] | GTC-A (ML) | 720 | 100% | - |  | GAS TURBINE COMPRESSOR MAIN LINE-A | 720 | 720 | 100% | -
[6 empty] | GTC-B (ML) | 720 | 100% | - |  | GAS TURBINE COMPRESSOR MAIN LINE-B | 720 | 720 | 100% | -
[6 empty] | GTC-C (ML) | 720 | 100% | - |  | GAS TURBINE COMPRESSOR MAIN LINE-C | 720 | 720 | 100% | -
[6 empty] | GTC-D (ML) | 720 | 100% | - |  | GAS TURBINE COMPRESSOR MAIN LINE-D | 720 | 720 | 100% | -
[6 empty] | GTC-E (ML) | 720 | 100% | - |  | GAS TURBINE COMPRESSOR MAIN LINE-E | 720 | 720 | 100% | -
[6 empty] | GTC-A (BL) | 432 | 60% | Engine Removed for Electric Drive |  | GAS TURBINE COMPRESSOR BRANCH LINE-A | 720 | 432 | 60% | Engine Removed for Electric Drive
[6 empty] | GTC-B (BL) | 720 | 100% | - |  | GAS TURBINE COMPRESSOR BRANCH LINE-B | 720 | 720 | 100% | -
[6 empty] | GTC-C (BL) | 720 | 100% | - |  | GAS TURBINE COMPRESSOR BRANCH LINE-C | 720 | 720 | 100% | -
[6 empty] | HVJ DEG | 720 | 100% | - |  | HVJ DIESEL EMERGENCY GENERATOR | 720 | 720 | 100% | -
[6 empty] | DVPL GTC-A | 720 | 100% | - |  | DVPL GAS TURBINE COMPRESSOR -A | 720 | 720 | 100% | -
[6 empty] | DVPL GTC-B | 552 | 76.67% | Engine Removed for Overhauling |  | DVPL GAS TURBINE COMPRESSOR -B | 720 | 552 | 76.67% | Engine Removed for Overhauling
[6 empty] | DVPL GTC-C | 720 | 100% | - |  | DVPL GAS TURBINE COMPRESSOR -C | 720 | 720 | 100% | -
[6 empty] | VDPL GTC-A | 672 | 93.33% | Bleed Valve Issue |  | VDPL GAS TURBINE COMPRESSORS-A | 720 | 672 | 93.33% | Bleed Valve Issue
[6 empty] | VDPL GTC-B | 720 | 100% | - |  | VDPL GAS TURBINE COMPRESSORS-B | 720 | 720 | 100% | -
[6 empty] | VDPL GTC-C | 0 | 0% | Engine sent for Overhauling |  | VDPL GAS TURBINE COMPRESSORS-C | 720 | 0 | 0% | Engine sent for Overhauling
[6 empty] | VDPL DEG | 720 | 100% | - |  | VDPL DIESEL ENGINE GENERATOR | 720 | 720 | 100% | -
[6 empty] | DVPL IAC-A | 720 | 100% | - |  | DVPL-INSTRUMENT AIR COMPRESSOR-A | 720 | 720 | 100% | -
[6 empty] | DVPL IAC-B | 720 | 100% | - |  | DVPL-INSTRUMENT AIR COMPRESSOR-B | 720 | 720 | 100% | -
[6 empty] | VDPL IAC | 672 | 93.33% | IA Comp. not delivering required pressure- |  | VDPL-INSTRUMENT AIR COMPRESSOR | 744 | 672 | 90.32% | Instrumentation Issue

## Crtical Spares
Plant | No. of Spares
| Adequate Qty (Qty > Min) | Threshold Qty (Qty = Min) | Insufficient Qty (Qty < Min)
C2C3 | 0 | 25 | 8
LPG | 6 | 16 | 6
HVJ | 13 | 26 | 11
List of Insufficient Critical Spares
|  |  |  | PLANT | MATERIAL CODE | DESCRIPTION | STATUS
|  |  |  | C2C3 | 1544010046 | DRY GAS SEAL SET - LGC HP COMP | PO Placed No. 5100004058. Complete Spares materials are expected to be received by Aug. 2024.
[5 empty] | 1537990010 | KE-1 SPARE ROTATING ASSEMBLY | SRA utilized in Shutdown in Apr-2024. Stripping of pulled out SRA done for spares assessment.
[5 empty] | 1191118390 | GAS GENERATOR SGT 700 | Readiness expected by Dec 24 through LTP. Stripping of GG required to ascertain spares requirement for overhauling.
[5 empty] | 1573020990 | RGC STEAM TURBINE SPARE ROTOR ASSLY | Material available in code 1573020998.
[5 empty] | 1512701350 | DRY GAS SEAL FOR PRC COMPRESSOR | DGS Sent for refurbishment under warranty to vendors work,
[5 empty] | 1125526310 | THRUST BEARING PAD FOR PRC TURBINE | PR Sent (PR No. 20119252) TBA Done.
[5 empty] | 1512701360 | JOURNAL BEARING ASS'Y WITH 3-RTD 5PAD/SET of THR END | PR Sent (PR No. 20119252) TBA Done.
[5 empty] | 1512701370 | JOURNAL BEARING ASS'Y WITH 3-RTD 5PAD/SET of JNL END | PR Sent (PR No. 20119252) TBA Done.
List of Insufficient Critical Spares
|  |  |  | PLANT | MATERIAL CODE | DESCRIPTION | STATUS
|  |  |  | LPG | 1174026110 | LEF GT ROTOR ASSY, L.P | Material Dispatched from vendor. EDD: Sept. 2024
[5 empty] | 1174026500 | LEF GT HP ROTOR ASSY | Material Dispatched from vendor. EDD: Sept. 2024
[5 empty] | 1174023140 | LEF GT TRANSITION PIECE | Material Dispatched from vendor. EDD: Sept. 2024
[5 empty] | 1174025800 | LEF GT ACCESSORY GEAR BOX | 1 Qty. Available at shop floor
[5 empty] | 1174025100 | CONVERTER, HYD, TORQUE | 1 Qty. Available at shop floor
[5 empty] | 1155120990 | LGC GT CAP & LINER ASSY | PR Sent (No. 20119667, Dt. 24.04.2024). PO to be placed.(02 Qty from Usar available at workshop.)
|  |  |  | HVJ | 1170101696 | M/L GG BRG,THRUST, | 1 Qty. Available at shop floor
[5 empty] | 1190113696 | M/L GG PUMP HYDRAULIC | 1 Qty. Available at shop floor
[5 empty] | 1190036346 | GTG STARTER,GAS,KB5, | 1 Qty. Available at shop floor
[5 empty] | 1190030203 | GTG PUMP,HYD, | On order stock
[5 empty] | 1190033444 | GTG BRG,RH SHFT,3.5IN DIA | 1 Qty. Available at shop floor
[5 empty] | 1190033454 | GTG BRG,LH SHFT,3.5IN DI | 1 Qty. Available at shop floor
[5 empty] | 1167107336 | PUMP,LO ASSY,EXCLUD CPLG,P/N-1014293-5 | 1 Qty. Available at shop floor
[5 empty] | 1580400203 | CRANK SHAFT,1721MM,P/N 35172090 | 1 Qty. Available at shop floor
[5 empty] | 1569030116 | VDPL GG SHAFT SEAL ASSM,DRY GAS, | 1 Set Sent for refurbishment. EDD: July-2024
[5 empty] | 1168030026 | VDPL POWER TURBINE ROTOR | 02 Nos available with location name 3018 NG Transmission - Noida . Physically at Vijaipur
[5 empty] | 1168030046 | VDPL GT FUEL NOZZLE ASSEMBLY | 2 Set Available at shop floor

## Statutory Compliances
Location | Equip. / Vessel | Governing Standard | Inspected On | Due on | Inspection Status
C2C3 Spheres | A | SMPV (U) Rules 2016 | 2022-11-11 | 2027-11-11 | Completed
| B |  | 2022-12-24 | 2027-12-24 | Completed
| C |  | 2023-02-10 | 2028-02-10 | Completed
LPG Spheres | A |  | 2023-02-25 | 2025-02-25 | Completed
| B |  | 2022-03-16 | 2027-03-16 | Completed
| C |  | 2022-12-27 | 2025-01-04 | Completed
| D |  | 2022-05-11 | 2027-05-11 | Completed
| E |  | 2022-11-03 | 2027-11-03 | Completed
| F |  | 2022-08-03 | 2024-08-08 | Completed
| G |  | 2023-05-10 | 2028-05-11 | Completed
| H |  | 24.02.2018 | 24.02.2023* | Repair to be done.
Propane Spheres | A |  | 2019-11-13 | 2024-11-13 | Completed
| B |  | 2020-02-21 | 2025-02-20 | Completed
| C |  | 2020-03-20 | 2025-03-20 | Completed
Naphtha Tanks | A | OISD 129 | 02.09.2013 | 02.02.2034* | Insulation U/P.
| B |  | 30.09.2013 | 29.09.2023* | Due
Location | Equip. / Vessel | Governing Standard | Inspected On | Due on | Inspection Status
Pentane Bullets | A | OISD 128 | 2021-01-05 | 2026-01-04 | Completed
| B |  | 2020-12-28 | 2025-12-27 | Completed
| C |  | 2020-12-19 | 2025-12-18 | Completed
| D |  | 2020-09-30 | 2025-09-29 | Completed
| E |  | 2020-09-25 | 2025-09-24 | Completed
N2 Bullets | A | SMPV (U) Rules 2016 | 02.06.2023 | 01.06.2028 | Completed
| B |  | 19.05.2023 | 18.05.2028 | Completed
Utility Boiler |  | IBR | 10.06.2024 | 10.06.2025* | Completed*
C2C3 HRSG Boiler | 1 |  | 13.04.2024 | 13.04.2025 | Completed
| 2 |  | 05.12.2023 | 11.12.2024 | Completed
| 3 |  | 13.04.2024 | 13.04.2025 | Completed
C2C3 HRSG Economiser | 1 |  | 13.04.2024 | 13.04.2026 | Completed
| 2 |  | 12.12.2022 | 11.12.2024 | Completed
| 3 |  | 03.04.2023 | 02.04.2025 | Completed
LPG Pack. Boiler |  |  | 13.04.2024 | 02.04.2025 | Completed
DVPL HRSG | A |  | 20.02.2023 | 19.02.2025 | Completed
| C |  | 08.09.2023 | 08.09.2025 | Completed
Remarks | 1. LPG Sphere H: Repair Job to be carried out. 2. Naptha Tank A: Insulation is U/P. 3. Naptha Tank B: Inspection to be done after completion of job in NapthaTank A. 4. Inspection and Testing of C2C3 Utility Boiler done on 10.06.2024

## Budget Utilization (hidden)
PLANT | BUDGET PROVISION |  | TOTAL UTILIZED | % UTILISATION
| RE 23-24 | BE 24-25
C2C3 | 3689 | 3622 | 2124 | 57.58%
LPG | 2546 | 1152 | 1845 | 72.47%
HVJ | 1986 | 2415 | 1596 | 80.36%

## GPU Equipment Overhauling
Sr. No. | Equipment | Running Hours @ End of June | Details of Last Inspection | Next Inspection Due | Inspection Overdue By: (Running Hours)
1 | LPG-11: LGC | 256047 | Combustion Inspection done in March 2023 at 249K R. H. | HGPI due at 262K R. H. | -5953
2 | LPG-12: LGC | 248625.19 | HGPI done in August 2023 at 243K R. H. | Major Inspection due at 259K R. H. | -10374.81
3 | LPG-11: PRU-1 | 173110.8233 | HGPI done in April 2022 at 166K R.H. | Major Inspection due at 178K R. H. | -4889.1767
4 | LPG-12: PRU-2 | 172569.45 | Extended HGPI (MI) done in September 2021 at 165K R. H. | Combustion Inspection due at 179K R. H. | -6430.55
5 | LPG-11: LEF-1 | 159513.4167 | Combustion Inspection done in September 2023 at 154K | HGPI due at 165K R. H. | -5486.5833
6 | LPG-12: LEF-2 | 150253.3333 | Combustion Inspection done in September 2022 at 143K R. H. | HGPI due at 156K R. H. | -5746.6667
7 | C2C3: LGC - A | 42199 | A-Type Inspection done in April 2024 at 40K R. H. | A-Type Inspection at 52K R. H. | -9801
8 | C2C3: LGC - B | 44779 | A-Type Inspection done in April 2024 at 42K R. H. | A-Type Inspection at 52K R. H. | -7221
9 | C2C3: LGC - C | 48324 | A-Type Inspection done in April 2024 at 46K R. H. | C-Type Inspection at 60K R. H. | -11676
10 | C2C3: PRC | 60477.8167 | Major Overhauling Steam Turbine done in Feb. 2023 at 50K R. H. | Minor Inspection due at 75K R. H. | -14522.1833

## HVJ Engine Status
Equipment | Make | Model | Installed Qty | Spare Qty | Healthy Qty | Overhauling Due for | Under Overhauling | Under Tendering
GAS GENERATOR | ALLISON | 501-KB5 | 8 | 2 | 8 | 2 | 0 | 2
| ALLISON | 501-KC5 | 28 | 5 | 26 | 6 | 1 | 3
| ROLLS-ROYCE | RB211 24G | 8 | 2 | 8 | 0 | 2 | 4
| ROLLS-ROYCE | RB211 24GT DLE | 10 | 0 | 8 | 1 | 1 | 0
| EGT TORNADO | SGT-200 | 2 | 1 | 2 | 0 | 1 | 0
POWER TURBINE | DRESSER RAND | GT-22C | 28 | 0 | 26 | 1 | 1 | 1
| ROLLS-ROYCE | RT-62 | 8 | 0 | 8 | 0 | 0 | 0
| ROLLS-ROYCE | RT-61 | 10 | 0 | 10 | 0 | 0 | 0
| EGT | SGT-200PT | 2 | 1 | 2 | 0 | 1 | 0
COMPRESSOR | ROLLS-ROYCE | RF3BB36 | 3 | 0 | 3 | 0 | 0 | 0
| ROLLS-ROYCE | RF2BB36 | 7 | 0 | 7 | 0 | 0 | 0
| DRESSER-RAND | CDP-416 | 28 | 0 | 28 | 0 | 0 | 0
| DRESSER RAND | DR452B3 | 2 | 0 | 2 | 0 | 0 | 0

## HVJ Engine Overhauling Status
Sr. No | Model | Serial Number | Compressor Station | Last Overhauled in | Status
1 | KB5 | ASP1689 | Jhabua | 2024 | Engine shifted to Vijaipur & received at Vijaipur on 24.05.2024
2 | KB5 | ASP1231 | Auraiya | 2024 | Engine received after overhauling in Auraiya.
3 | KC5 | ASP1822 | Hazira | 2024 | Engine received after overhauling in Hazira on 11.06.2024
4 | KC5 | ASP1208 | Hazira | 2024 | Engine received after overhauling in Hazira on 08.06.2024
5 | KC5 | ASP1981 | Hazira | - | Engine builtup is under progress at vendor's work
6 | KB5 | ASP1860 | Jhabua | 2015 | Tendering stage, Price bid opened.
7 | KB5 | ASP2094 | Auraiya | 2009 | Tendering stage, Price bid opened.
8 | KC5 | ASP1216 | Hazira | 2004 | Tendering stage, Price bid opened.
9 | KC5 | ASP1225 | Hazira | 2010 | Tender floated, bid submission due date is 29.07.2024
10 | KC5 | ASP1980 | Hazira | 2011 | Tender floated, bid submission due date is 29.07.2024
11 | KC5 | ASP1734 | Vijaipur | 2003 | Tender floated, bid submission due date is 29.07.2024
12 | RB211 24GT DLE | 1890-2046 | Vijaipur | - | Performance test is scheduled on 08.07.2024
13 | RB211 24GT DLE | 1890-2048 | Vijaipur | - | Engine to be sent after receipt of 1890-2046
14 | Solar Titan130S | 0082L | Vijaipur | 2024 | Engine installed & comissioned at DVPL GTC-C
15 | Solar Titan130S | 0081L | Vijaipur | 2011 | Engine Removal work is under progress.
16 | GT-22C | T-5551 | Auraiya | 2020 | Warranty repair, PT dismantled, warranty claim negotiation is in progress
17 | GT-22C | T-5555 | Vijaipur | - | After negotiation on revised offer, vendor has submitted its response.

## Long Term Jobs
Sr. No. | DESCIRPTION | JOB STATUS | PHOTO
1 | Pre-Feasibility Study for Electrificatin of NG Driven Equipment at GPU Vijaipur | 1. Draft Report submitted by EIL and Queries discussed through meeting. 2. Final Report awaited from M/s EIL.
2 | Installation of GWR LTs in LPG & Propane Spheres | 1. GWR commissioned in LPG Sphere A, B, C, D, E, F, G. Contract for sphere inspection lined up and LOA awarded to M/s TMC. 2. Commissioning of GWR in Propane spheres A, B and modification in Propane sphere C to be done during statutory inspection. 3. Commissioning work of LPG Sphere-H to be done along with repair of sphere.
3 | Condition assesment of LPG & Propane Horton Spheres | Reports & Repair procedure for Plate weld received from M/s EIL. Repair Methodology finalisation is under discussion with PESO. Quotation sought from vendors for lining up contract for repair works.
4 | C2C3 & LHC Product Rnhancement | 1. Chiller: TQ reply received from 1 bidder M/s Sumitomo. TQ-2 raise to bidders. 2. Composite works: Proposal already initiated for additional investment approval. 3. Vessels - Delivery expected by Aug’24 4. Valves Delivered against PO: 5700048768. Documentation work under progress..
5 | Guillotine Shutter cum Diverter Damper for Tighter Sealing | Virtual Meeting with M/s Thermax done on 07.06.2024 for expediting testing and delivery. Internal review meet conducted on 25.07.2024 with Operations & other maintenance departments. Performance Testing at vendors works is scheduled in July 2024.
6 | Comprehensive Tank Farm Shutdown of LPG Storage area | 1.Valves procurement - Ball valve:- M/s NITON VALVES PRIVATE LIMITED, Ahmedabad. Material partly delivered. PO No. 5700051760 EDD: 30.09.2024
7 | Table Top Study of M/s Siemens | All 03 Sites reports received, review and comments being done.
8 | Flare Tip Refurbishment | Report on visual inspection of pulled out flare tip recived from vendor.
Sr. No. | DESCIRPTION | JOB STATUS | PHOTO
9 | CBD Project | 1.Pumps, PO: 5800005468 Placed to M/s KSB, CDD: 04.08.2024, QAP approved, detailed engineering in process. 2.CBD vessel, PO : 5700051457 placed to M/s Udkam Process Equipments,Drawing & QAP approved, EDD - Sept 2024 3.For composite works : Price part recieved from EIL for estimate preparation. Query from Mechanical resolved, Query from Electrical & Instrument is under resolution.
10 | Borewell Piping Layout | Job Completed. Approx. 1.7 km pipeline laying done at site.
11 | Siemens LTP for SGT -700 | Meeting with M/s Siemens done on 03-06-2024 regd. issues with LTP. Followup meeting to be planned.
12 | C2C3 LGC-A Pulled out GG Readiness | Activity list for dismantling of pulled out GG is ready. Spares requirement for refurbishment to be made after GG stripping.
13 | C2C3 KE-1 SRA Refurbishment | Budgetary quotoation received from vendor in which quoted prices are very high. Discussion for review of prices is under progress.
14 | Expander Compressor After Cooler Procurement | 1) PO placed, LOA: 5700052564 Dated : 21.03.2024 2) QAP approved on 29.05.2024 and drawings are under review.
15 | FR-3 Exhaust Revamping | PO: 5300039015 placed to M/s BGGTS on 16.06.2023 with CDD 15.06.2025 i) Vendor's Site visit (for duct measurement) conducted in May 2024 ii) Silencer duct received at site in June 2024, EDD for balance materials Aug 2024.
16 | FR-3 GT (Usar) Rotor & HGP Component Refurbishment | Budgetary quotation and scope of work to be received from OEM.
17 | Services for Failure Mode Analysis | Seeking Bugdgetary Qoutation from prospective Bidders (E-Mail communication in this regard done)

## ai (hidden)
S No. | Standard | Description | Scheduled/ Ongoing
1 | OISD-STD-128 | NDT & Pneumatic Testing of PSA N2 Surge Vessels-A/B/C in IA/IG Plant | Jan 2024 - Completed
2 | OISD-STD-130 | Visual, UTG & LRUT of Feed Gas & Lean Gas lines, RLNG line, Amine Loop | Jan 2024 - Completed
3 | OISD-STD-128 | NDT of LP Air Receiver and HP Air Receiver in IA/IG Plant | Feb 2024 - Completed
4 | OISD-STD-128 | Comprehensive NDT Inspection of Pr. Vessel - Side Stream Filter (25-GN-001 A/B) | Mar 2024 - Completed
5 | OISD-STD-128 & OISD-STD-130 | Statutory Inspection of Process Pipelines, Pressure vessels & Lifting Tools | Apr 2024 - Completed
1 | OISD-STD-128 | Comprehensive NDT Inspection of Pr. Vessels - Water Seal Drum (63-VV-003), Deaerator (34-VV-002) | Apr 2024 - Completed
2 | OISD-STD-134 | NDT Inspection of 36 No.s Air Fin Coolers at C2C3 Plant | Apr 2024 - Completed
3 | OISD-STD-134 | NDT Inspection of 51 No.s Heat Exchangers at C2C3 Plant using ECT, RFT & PAUT Techniques . | Apr 2024 - Completed
4 | OISD-STD-128 | Advanced NDT Inspection of 24 No.s Pr. Vessels & Columns using UTG & PECT – External & Internally | Apr 2024 - Completed
5 |  | Scanning of Dryer Lines near MOVs by PECT Technique at 13 Locations | Apr 2024 - Completed
6 | OISD-STD-130 | LRUT of Approx. 3925 m Process Piping at C2C3 Unit Area | Apr 2024 - Completed
7 | OISD-STD-133 | Inspection of All 48 No.s Regeneration Gas (RG) Heater Tubes (Tag No.. 18-FF-101) using UTG, PECT, LRUT, Hardness Test | Apr 2024 - Completed
8 | MP Factories Rules 1962 & OISD STD 129 | Inspection of Spent Amine Tank using UTG - External & Internally along with External Painting | Apr 2024 - Completed
9 | OISD-STD-129 | NDT Inspection of DM Water Tank - B at C2C3 DM Plant (Internal) | May 2024 - Under Progress
10 | OISD-STD-130 | LRUT/ SRUT of Approx. 2700 m Process Pining at LPG Unit Area | May 2024 - Completed
11 | OISD-STD-129 | NDT Inspection of DM Water Tank - B at C2C3 DM Plant (External) | June 2024 - Completed

## Asset Integrity
S No. | Standard | Description | Status & Photo |  | Photo
1 | OISD-STD-128 | NDT & Pneumatic Testing of PSA N2 Surge Vessels-A/B/C in IA/IG Plant | Jan 2024 - Completed
2 | OISD-STD-130 | Visual, UTG & LRUT of Feed Gas & Lean Gas lines, RLNG line, Amine Loop | Jan 2024 - Completed
3 | OISD-STD-128 | NDT of LP Air Receiver and HP Air Receiver in IA/IG Plant | Feb 2024 - Completed
4 | OISD-STD-128 | Comprehensive NDT Inspection of Pr. Vessel - Side Stream Filter (25-GN-001 A/B) | Mar 2024 - Completed
5 | OISD-STD-128 & OISD-STD-130 | Statutory Inspection of Process Pipelines, Pressure vessels & Lifting Tools | Apr 2024 - Completed
1 | OISD STD-128 | Comprehensive NDT Inspection of Pr. Vessels - Water Seal Drum (63-VV-003), Deaerator (34-VV-002) | Apr 2024 - Completed
1 | OISD STD-134 | NDT Inspection of 34 No.s Air Fin Coolers at C2C3 Plant | Apr 2024 - Completed
2 | OISD STD-134 | NDT Inspection of 51 No.s Heat Exchangers at C2C3 Plant using ECT, RFT & PAUT Techniques . | Apr 2024 - Completed
3 | OISD STD-128 | Advanced NDT Inspection of 24 No.s Pr. Vessels & Columns using UTG & PECT – External & Internally | Apr 2024 - Completed
4 | OISD STD-128 | Scanning of Dryer Lines near MOVs by PECT Technique at 13 Locations | Apr 2024 - Completed
5 | OISD STD-130 | LRUT of Approx. 3925 m Process Piping at C2C3 Unit Area | Apr 2024 - Completed
S No. | Standard | Description | Status | Photo | Photo
6 | OISD STD-133 | Inspection of All 48 No.s Regeneration Gas (RG) Heater Tubes (Tag No.. 18-FF-101) | Apr 2024 - Completed
7 | MP Factories Rules 1962 & OISD STD-129 | Inspection & Internal Painting of Spent Amine Tank using UTG - External & Internally | Apr 2024 - Completed
8 | OISD STD-130 | LRUT/ SRUT of Approx. 2700 m Process Pining at LPG Unit Area | May 2024 - Completed
9 | OISD STD-129 | NDT Inspection of DM Water Tank - B at C2C3 DM Plant (External) | June 2024 - Completed
10 | OISD STD-128 | Inspection & RLA of N2 buffer vessel, IA receiver vessel, PA receiver vessel in LPG Offsites | June 2024 - Completed

## MOC OLD (hidden)
MOC NO. | DESCRIPTION | JOB STATUS
1261 | M/L AND B/L VENT LINE SHIFTING | 1. Painting work completed and site clerance done. Lines handover to operation for further use. 2. Followed with operation department for closing of MOC in system.
991 | FUEL GAS FROM RLNG TO MP FOR VDPL COMPRESSORS | 1. Approx. 450 Meter Pipes laying done 2. 100 Joints Welding done. 3. 100% RT done 4. Hydrotest carried out at 138 Kg/cm2 5. Project Commissioned 6. MOC closed from execution side
2561 | Supply of RLNG from DVPL-I to NFL Vijaip | 1. Tender floated 2. RFQ done 3. TBA Done 4. LOA awarded 5. IRN received for fittings and pipes PR Clubbed with MOC 2561 i.e. Supply of RLNG from DVPL-I to NFL VIJAIPUR
MOC NO. | DESCRIPTION | JOB STATUS
2807 | Utility Corridor for HVJ compressor station | 1. Tender floated 2. RFQ done 3. TBA Done 4. LOA awarded PR Clubbed with MOC 2561 i.e. Supply of RLNG from DVPL-I to NFL VIJAIPUR
1385 | IA HOOK UP FROM GPU TO HVJ CS | Completed & commissioned. Below activity carried out: 02 Inch line hook-up to dryer inlet. Required NRVs, Valves & Gauge installed Commissioned with mesh strainer with inspection
1262 | BYPASS LINE FOR HP-MP PCV OF NFL LINE | Completed & Commissioned on 08.05.2023. Below activity carried out in NFL PCV skid modification. 1. Modification of PCVs skid 2. Hook-up with existing headers 3. RT test of all joints -25 Joints 4. Hydrotest of complete loop – 138 Kg/cm2 5. Cardboard blasting of total loop – Blasting done in 02 loops till satisfactory parameters 6. 02 Nos PCVs installation. 7. Painting of skid & pipes – Primer & 02 coat paint applied 8. Final De-Blinding – Leak test done after nitrogen purging 9. Commissioning done with HP gas entry. No leak found.
MOC NO. | DESCRIPTION | JOB STATUS
1413 | HOOK-UP OF PLANT AIR FROM GPU TO HVJ | Completed & commissioned. Below activity carried out: 06 Inch line hook-up to discharge header. Required NRVs, Valves, Flow Orifice, Gauge installed Commissioned with mesh strainer with inspection.
2254 | PROVIDING BYPASS FOR AV6118 | Project kept on Hold by Chair Person CGM(O&M)
671 | HP-MAIN LINE CONNECTIONS | Project kept on Hold by Chair Person CGM(O&M)
1824 | REMOVAL OF 14”UNFILTERED RLNG LINE | Completed and Handover to operation
2226 | MODIFICATION FOR VAPL PIPELINE CONNECTION | Job carried out by construction team
| FCV INSTALLATION IN VAPL LINE | Site visit done by M/s LEPL PMC , required reports preparation is in progress.
| VDPL VENT RECOVARY TO GTGS FUEL | 1. PMC services hired. 2. P&ID revsion-1 received and found as per requirement. 3. HAZOP Study to be done

## MOC Jobs
MOC NO. | DESCRIPTION | JOB STATUS
1261 | M/L and B/L Vent Line Shifting | 1. Painting work completed and site clerance done. Lines handover to operation for further use. 2. Followed with operation department for closing of MOC in system.
991 | FUEL GAS FROM RLNG TO MP FOR VDPL COMPRESSORS | 1. Approx. 450 Meter Pipes laying done 2. 100 Joints Welding done. 3. 100% RT done 4. Hydrotest carried out at 138 Kg/cm2 5. Project Commissioned 6. MOC closed from execution side
2561 | Supply of RLNG from DVPL-I to NFL Vijaip | 1. Tender floated; 2. RFQ done; 3. TBA Done; 4. LOA No -5700052935 dated 09.05.2024 awarded, 5. Inspection Release note received for fittings and pipes 6. PR Clubbed with MOC 2807 i.e. Utility Corridor for HVJ compressor station 7. Material Under manufacturing with vendor
2807 | Utility Corridor for HVJ compressor station | 1. Tender floated; 2. RFQ done; 3. TBA Done; 4. LOA 5700052936 dated 09.05.2024 awarded, 5. PR Clubbed with MOC 2561 i.e. Supply of RLNG from DVPL-I to NFL VIJAIPUR 6. Material Under manufacturing with vendor- 7. 2 inch Gate valve to be procured by re-tendering
1385 | IA HOOK UP FROM GPU TO HVJ CS | Completed & commissioned. Below activity carried out: 02 Inch line hook-up to dryer inlet. Required NRVs, Valves & Gauge installed Commissioned with mesh strainer with inspection
1262 | BYPASS LINE FOR HP-MP PCV OF NFL LINE | Completed & Commissioned on 08.05.2023. Below activity carried out in NFL PCV skid modification. 1. Modification of PCVs skid 2. Hook-up with existing headers 3. RT test of all joints -25 Joints 4. Hydrotest of complete loop – 138 Kg/cm2 5. Cardboard blasting of total loop – Blasting done in 02 loops till satisfactory parameters 6. 02 Nos PCVs installation. 7. Painting of skid & pipes – Primer & 02 coat paint applied 8. Final De-Blinding – Leak test done after nitrogen purging 9. Commissioning done with HP gas entry. No leak found.
1413 | HOOK-UP OF PLANT AIR FROM GPU TO HVJ | Completed & commissioned. Below activity carried out: 06 Inch line hook-up to discharge header. Required NRVs, Valves, Flow Orifice, Gauge installed Commissioned with mesh strainer with inspection.
2254 | Providing Bypass for AV6118 | Project kept on Hold.
671 | HP-Main Line Connections | Project kept on Hold. Closure under progress by concern department
1824 | REMOVAL OF 14”UNFILTERED RLNG LINE | Completed and Handover to operation
2226 | Modification for VAPL Pipeline Connections | Job carried out by construction team
1385 | IA HOOK UP FROM GPU TO HVJ CS | Completed & commissioned. 02 Inch line hook-up to dryer inlet. Required NRVs, Valves & Gauge installed Commissioned with mesh strainer with inspection
| VDPL vent Recovery to GTGS Fuel | 1. PMC services hired. (Child PO GAIL/4000007328/5300041153/NOID/23124 DATED 10.05.2024 2. P&ID reviewd by multidepartment and revsion-1 received from PMC and found as per requirement. 3. HAZOP Study to be done.; 4. Design Basis preparation under progress
| FCV Installation in VAPL Line | PMC involvement Format signed and forwarded to concern team , Child PO GAIL/4000007328/5300042342/NOID/23124 dated 18.07.2024 to be awarded to PMC M/s Lyons
| LP Fuel Gas to HRSG Burner | Job Completed
| 4 inch FGRU to Fuel Gas Interconnection | Job Completed
MOC NO. | DESCRIPTION | JOB STATUS
1231 | 6" Line from SEP-2 to CC-102 Feed line | Job Completed
1402 | Interconnection between 12-VV-110 & 18-VV-116 | Material received, elbows are under TPI stage. Job will be commenced through MOC contract.
1735 | Provision of isolation valve in process side of C2C3 Re-boiler (18-EE-114) | Material PO placed. Expected delivery Sept 2024.
1736 | Increasing 18-EE-103 FG B/P Line Size | 24 inch by-pass line Job already completed. Control valve with manual gate valves will be installed during next plant shutdown.
1852 | Modification of CT2 & CT3 CW Interconnection | Request for budgetary quote forwarded. File will be initiated soon.
1981 | Interconnection of C2C3 BOG to LEF | Material received. Line fabrication & erection near battery limit is under progress.
2175 | MOC for CPU ACF Backwash Process | Job Completed
2292 | Laying LP steam header from LPG for HVAC | Design job completed. File will be initiated in Aug 2024 month.
2643 | Laying new 24-inch line from GSU Coalescer filter (16-GN-104) Outlet to GPU Suction KOD (18-VV-101) | Tapping job completed. Fittings received. Piping delivery expected: July'24 1st week. Check valve : Material Received. 24 inch gate valves : EDD: Sept'24 04 nos. 45 degree elbow PATA , STO done. Expected delivery by 20th Aug 2024.
1824 | REMOVAL OF 14”UNFILTERED RLNG LINE | Completed and Handover to operation.
| 16-inch by-pass for propane chiller 18-EE-105 | Material PO placed. Pipe and fittings : July'24. Valves : Sept'24
| New 24-inch by-pass line for heat exchangers 18-EE-103 A/B/C | Job to be done in Shutdown opportunity.

## R&D Projects
SR NO. | DESCIRPTION | JOB STATUS
1 | Updation/ Retrofit of Wet Seal to Dry Gas Seal in Dressor Rand Make CDP 416 Compressor | Technical datas have been provided to vendor for techno-commercial offer
2 | Electrical Motor Drive (Prime Mover) for HVJ Compressor Package (One machine in Branch Line) | Compressor suction -12 inch and Discharge -10 Inch line & bypass line of 1 Inch positive blinding done. Removal of Air intake filter part, air intake inertia fan section, silencers section and enclosure fan housing. Total Air intake filters removed in 02 parts with all in usable/spare condition. Power Turbine removed from skid and kept in workshop with stand for spare use Removal of lines/piping like Instrument Air, hoses, GG lube oil breather, GG enclosure drain, PT drain, lube oil tank drain, starter outlet flanged etc. Scaffolding erection extended to 15 x3x3 m height to access stack height Top portion of stack removed from flange connection. 2nd /Middle portion of stack removed o damper top with silencer inside it. Damper flanged removed from PT top stack duct. GG & PT enclosure removed from base frame Lube oil draining of PT & Compressor section i.e. Mineral Oil
3 | Detailed engineering, design, manufacturing, supply, installation & commissioning of new diverter damper and guillotine shutter wall in Lean Gas Compressor (LGC) at C2C3 Recovery Plant | Virtual meeting with M/s Thermax conducted on 07.06.2024 for regarding expediting the testing process. Performance Testing at vendors works is planned in August 2024.
4 | Installation of FCV in VAPL in order to maintain hydraulics of VAPL & JHBDPL network without compromising lean gas evacuation | Format-I approval done for PMC service line-up from CIMG team.